TABLE OF CONTENTS

SECTION I - SPECIAL INFORMATION FOR BIDDERS	3

SECTION II – OFFER TO CONTRACT	5

SECTION III - CONTRACTOR'S BID FORMS	9

SECTION IV - CONTRACTOR'S CONTRACT FORMS	14

SECTION V - SPECIAL CONDITIONS	19

SECTION VII – PREVAILNG WAGES	47

CITY OF BATTLE CREEK, MICHIGAN
NOTICE OF INVITATION FOR BIDS

2018 CITY OF BATTLE CREEK WATER MAIN PROJECT

IFB # 2018-058B

IFB DUE DATE and TIME:  March 20, 2018, at 2:00 pm local time (office hours 8-12 and 1-5) NOTE!  City Hall now has Security on the 1st floor.  Please allow extra time to get through Security when dropping off your bid.

BID SUBMITTAL:  Bids must be submitted in a sealed envelope with the IFB number, the due date/time and the bidder's name and address clearly indicated on the envelope. Bids must be in the actual possession of the Purchasing Department Room 214, City Hall, 10 N. Division Street, Battle Creek, Michigan 49014 on or prior to the exact time and date indicated above. The prevailing clock shall be www.time.gov.   Late bids will not be considered. All bids will be publicly opened and read aloud at the aforementioned address.  All interested parties are invited to attend.

PROJECT DESCRIPTION: The City of Battle Creek will accept sealed bids for the 2018 City of Battle Creek Water Main project.  This project consists of, but is not limited to pavement replacement of ±12,425 lineal feet of roadway including ±7,779 tons of HMA, ±7,334 square feet of concrete surface replacement, ±1,740 lineal feet of concrete curb and gutter replacement, ±8,066 lineal feet of water main replacement and associated work items.

DRAWINGS ARE AVAILABLE ON OUR WEBSITE: http://mi-battlecreek.civicplus.com/230/Bid-Proposal-Solicitations

Follow the link for Bid & Proposal Solicitations.

| PRE-BID CONFERENCE: NONE | FUNDING: This project has NO federal or state funding. All project funding is provided by the City of Battle Creek. None of the CDBG requirements are applicable for this contract. |
| --- | --- |
| TECHNICAL QUESTIONS OR SITE VISITATION: Kurt Tribbett/Tab McCrumb 269-966-3343 | PREVAILING WAGES: Required for this project. See attached wage rates at the end of this document. Contractor shall abide by all the requirements set forth in Section 208.09, PREVAILING WAGES ON CITY PROJECTS, of the City’s Administrative Code. |
| COPIES OF IFB: Available online only at http://mi-battlecreek.civicplus.com/230/Bid-Proposal-Solicitations Follow the link for Bid & Proposal Solicitations | FEE: No fee. DRAWINGS ARE AVAILABLE ON OUR WEBSITE: http://mi-battlecreek.civicplus.com/230/Bid-Proposal-Solicitations Follow the link for Bid & Proposal Solicitations. |
|  | IFB ISSUE DATE: February 15, 2018 |
| DOCUMENT EXAMINATION: Available online only at http://mi-battlecreek.civicplus.com/230/Bid-Proposal-Solicitations Follow the link for Bid & Proposal Solicitations | ADDENDA: Each addendum will be on file in the Office of the Purchasing Agent. To the extent possible, copies will be mailed to each person registered as having received a set of bid documents. It shall be the bidder's responsibility to make inquiry as to addenda issued. All such addenda shall become a binding part of the contract. |
| BID BOND: Each bid must be accompanied by a certified check, cashier's check, or standard form bid bond, made payable to the City of Battle Creek, in an amount of not less than five (5%) percent of the base bid submitted. Failure of any accepted bidder to enter into a contract for the work will cause forfeit of the bid security. After contracts for the work have been signed, all bid securities will be returned. | PERFORMANCE/LABOR/MATERIALS BONDS: The accepted bidder will be required to furnish a satisfactory performance bond and labor/materials payment bond, each in an amount equal to 100% of the contract and insurance certificate upon forms acceptable to the City. |
| BID VALID: Bids may be withdrawn up to the time and date of the bid opening. After the bid opening, bids may not be withdrawn for a period of ninety (90) days thereafter. The City of Battle Creek reserves the right to waive any irregularity or informality in bids, to reject any and/or all bids, in whole or in part, or to award any contract to other than the low bidder, should it be deemed in its best interest to do so. |  |

# SECTION I - SPECIAL INFORMATION FOR BIDDERS

1. General Contract Specification

The following sections of the General Contract Specifications BC-19-08, will be applicable for this contract General Instructions to Bidders and General Conditions of City Contracts.

2. Order Of Precedence

The plans and specifications shall be considered to be one complete document and what is called for in one shall be considered as being called for in all. In the event that there is a conflict between the parts, the following order of precedence shall govern:

Addenda to bidding documents

The Contract Drawings

The Contract Special Provisions

The Contract Special Instructions

The Contract Special Conditions

The City of Battle Creek General Contract 19-08

3. Special Conditions

The purpose of Special Conditions, Special Instructions, and Project Specifications are to change, delete, clarify or add to General Conditions, General Instructions or General Specifications found in GENERAL CONTRACT SPECIFICATIONS BC 19-08, issued 1998. Only those items addressed in Special Conditions, Special Instructions, or Project Provisions are affected.  All other conditions in General Conditions, General Instructions and General Specifications still apply.  Special Conditions, Special Instructions, Project Specifications, supersedes General Conditions, General Instructions and General Specifications, and in all cases shall take precedence.

4. Registration Requirements for Contractors

All bidders, including General Contractors and Specialty Contractors, shall hold or obtain such Contractors or Business Licenses as required State and Local statues.

5. Currency

Prices calculated by the bidder shall be stated in U.S. dollars.

6. Unit Price

When the Bid for the work is to be submitted on a unit price basis, unit price Bids will be accepted on all items of work set forth in the Bid, except those designated to be paid for as a lump sum. The estimated of quantities of work to be done is tabulated in the Bid and although stated with as much accuracy as possible, are approximate only and is assumed solely for the basis of calculation upon which the award of Contract shall be made. Payment to the Contractor will be made on the measurement of the work actually performed by the Contractor as specified in the Contract Documents. Unit prices will prevail in event of discrepancy and in bid tabulations.

7. Liquidated Damages

Failure of the Contractor to complete the work within the time allowed will result in damages being sustained by the City. Such damages are, and will continue to be, impracticable and extremely difficult to determine. Unless otherwise provided in the Special Conditions, the Contractor will pay to the City for the liquidated damages and not as penalty Five hundred dollars ($500.00) for each calendar day of delay in finishing the work in excess of the time specified for completion, plus any Contractor will pay the City for the liquidated damages herein before mentioned are in lieu of the actual damages arising from such breaches of this contract; which said sums the City shall have the right to deduct from any monies in its hands, otherwise due, or to become due, to said Contractor or to sue for and recover compensation or damages for non performance of this Contract at the time stipulated herein and provided for. The attention of bidders is directed to the provisions and the General Conditions of contract requiring the Contractor to pay for all excess cost of field engineering and inspection as therein defined.

8. Listing of Subcontractors

Failure to list subcontractors and major suppliers, where feasible, may be cause for rejection of the Bidder's Bid as non-responsive.

9. Non-collusion:

By signing the Offer to Contract, the bidder, by its officers and authorized agents or representatives present at the time of filing this bid, being duly sworn on their oaths say, that neither they nor any of them have in any way, directly or indirectly entered into any arrangement or agreement with any other bidder or with any public officer of such City of Battle Creek, Michigan, whereby such affidavit or affiants or either of them has paid or is to pay to such other bidder or public officer any sum of money, or has given or is to give to such other bidder or public officer anything of value whatever, or such affidavit or affiants or either of them has not directly or indirectly, entered into any arrangement or agreement with any other bidder or bidders, which tends to or does lessen or destroy free competition in the letting of the contract sought for by the attached bids, that no inducement of any form or character other than that which appears on the face of the bid will be suggested, offered, paid or delivered to any person whomsoever to influence the acceptance of the bid or awarding of the contract, nor has this bidder any agreement or understanding of any kind whatsoever, with any person whomsoever to pay, deliver to, or share with any other person in any way or manner, any of the proceeds of the contract sought by this bid.

10. 	Contractor’s Insurance

- The Contractor shall at the time of execution of this contract, file with the City the Certificate of Insurance, which shall cover all of his insurance as required herein, including evidence of payment of premiums thereon, and the policy or policies or insurance covering said City and their officers, agents and employees. Each such policy and certificate shall be satisfactory to the City. Nothing contained in these insurance requirements is to be construed as limiting the extent of the Contractor's responsibility for payment of damages resulting from his operations under this Contract.  The contractor shall maintain insurances in force at all times during the term of this agreement at the minimum amounts and types as indicated.

Coverage Afforded										Limits of Liability

Workers' Compensation:   									$   100,000 or statutory limit

Commercial General Liability: 	Bodily Injury 					$1,000,000 each occurrence

(including XCU if appropriate)	Property Damage 			$1,000,000 each occurrence

or Combined Single Limit	$2,000,000

Automobile Liability: 			Bodily Injury					$   300,000 each person

Liability					$   500,000 each occurrence

Property Damage	 		$   500,000

or Combined Single Limit	$   500,000

The City of Battle Creek shall be listed as an additional insured on general liability coverage, and shall be provided with a Certificate of Insurance that reflects this additional insured status. A 30-day notice of cancellation or material change shall be provided to the City and so noted on the Certificate of Insurance. All certificates and notices shall be sent to City of Battle Creek, 10 N. Division, Suite 214, Battle Creek, MI 49014.

11.  Vendor Evaluation:  Experience with the City shall be taken into consideration when evaluating responsibility of the vendor.

12. Permits:  Contractor shall secure all necessary permits to complete the work as described in this IFB.  These costs shall be included in the bid price.

13. Michigan Constitutional Requirement:

a). Notwithstanding any provision in this Contract to the contrary, and in accordance with Article I, Section 26 of the Michigan Constitution as adopted by the electorate November 7, 2006, the City and its general contractors shall not discriminate against, or grant preferential treatment to, any individual or group on the basis of race, sex, color, ethnicity, or national origin in the operation of this Contract.

b).  This section shall not prohibit any action that must be taken to establish or maintain eligibility for any federal program if ineligibility would result in a loss of federal funds in connection with this Contract, nor shall this section be interpreted as prohibiting bona fide qualifications based on sex that are reasonable necessary to the execution of this Contract.

c). In the event of conflict between any term of this Contract and this section, the language of this section shall control.

d)	"Any party bringing a legal action or proceeding against any other party arising out of or relating to this Agreement or the transactions it contemplates shall bring the legal action or proceeding: (i) in the United States District Court for the Western District of Michigan; or (ii) in any court of the State of Michigan sitting in Calhoun County, if there is no federal subject matter jurisdiction."

# SECTION II – OFFER TO CONTRACT

DATE:

NAME OF BIDDER:

BUSINESS ADDRESS:

To: The City of Battle Creek, Michigan

The undersigned, as Bidder, declares that the only person or parties interested in this bid as principals are those named herein; that this bid is made without collusion with any person, firm or corporation; that he has carefully examined the location of the proposed work, the proposed forms of Agreement and Bonds, and the Contract Drawings and Specifications for the above designated work, all other documents referred to or mentioned in the Contract Documents, the Contract Drawings and Specifications, including Addenda issued thereto; and he proposes and agrees if this bid is accepted that he will contract with the City of Battle Creek, Michigan, in the form of the copy of the Agreement included in these Contract Documents, to provide all necessary machinery, tools, apparatus, and other means of construction, including utility and transportation services necessary to do all the work and furnish all materials and equipment specified or referred to in the Contract Documents, in the manner and time therein prescribed and according to the requirements of the City of Battle Creek, Michigan, as therein set forth and to furnish the Contractor's Bonds and Insurance, and to do all other things required of the Contractor by the Contract Documents, and that he will take in full payment therefore the sums set forth BELOW;

A bid must be made on each item with no qualifying statement(s).  Bidder acknowledges that quantities are not guaranteed and final payment will be based on actual quantities determined as provided in the Contract Documents.  All specific cash allowances are included in the prices set forth below and have been computed in accordance with the Contract Documents.

Acknowledgement of addenda: _______; _______; _______; _______; ________; ________

2018 CITY OF BATTLE CREEK WATER MAIN PROJECT – PRICE SHEET

| ITEM NO. | DESCRIPTION | UNITS | EST. QTY. | UNIT PRICE | ITEM TOTAL |
| --- | --- | --- | --- | --- | --- |
| 1 | Mobilization, Max 5% | LSUM | 1 |  |  |
| 2 | Maintaining Local Traffic | LSUM | 1 |  |  |
| 3 | Barricade, Type III, High Intensity, Double Sided, Lighted, Furn | Ea | 56 |  |  |
| 4 | Barricade, Type III, High Intensity, Double Sided, Lighted, Oper | Ea | 56 |  |  |
| 5 | Plastic Drum, High Intensity, Furn | Ea | 239 |  |  |
| 6 | Plastic Drum, High Intensity, Oper | Ea | 239 |  |  |
| 7 | Sign, Type B, Temp, Prismatic, Furn | Sft | 985.5 |  |  |
| 8 | Sign, Type B, Temp, Prismatic, Oper | Sft | 985.5 |  |  |
| 9 | Erosion Control, Inlet Protection, Fabric Drop | Ea | 85 |  |  |
| 10 | Curb and Gutter, Rem | Ft | 5492 |  |  |
| 11 | Sidewalk Rem, Modified | Syd | 1086 |  |  |
| 12 | Hot Mix Asphalt Base Crushing and Shaping, Modified | Syd | 42923 |  |  |
| 13 | Machine Grading | Sta | 124.25 |  |  |
| 14 | Subgrade Undercutting, Type II | Cyd | 239 |  |  |
| 15 | Maintenance Gravel, LM | Cyd | 235 |  |  |
| 16 | Dr Structure Cover, Adj, Case 1 | Ea | 81 |  |  |
| 17 | Dr Structure Cover, Type B | Ea | 34 |  |  |
| 18 | Dr Structure Cover, Type Q | Ea | 47 |  |  |
| 19 | Dust Control | Ea | 25 |  |  |
| 20 | HMA, 13A | Ton | 7779 |  |  |
| 21 | Hand Patching | Ton | 91 |  |  |
| 22 | Curb and Gutter, Conc, Det F4 | Ft | 5466 |  |  |
| 23 | Driveway, Nonreinf Conc, 6 inch | Syd | 232 |  |  |
| 24 | Sidewalk, Conc, 6 inch | Sft | 860 |  |  |
| 25 | Sidewalk, Conc, 4 inch | Sft | 6474 |  |  |
| 26 | Pavt Mrkg, Thermopl, 6 inch, Crosswalk | Ft | 1147 |  |  |
| 27 | Pavt Mrkg, Thermopl, 24 inch, Stop Bar | Ft | 322 |  |  |
| 28 | Turf Establishment, Special | Syd | 4679 |  |  |
| 29 | Tree, Rem, 19 inch to 36 inch | Ea | 22 |  |  |
| 30 | Acer rubrum, 2 inch | Ea | 22 |  |  |
| 31 | Water Service, Rem | Ea | 260 |  |  |
| 32 | Water main, Rem | Ea | 11450 |  |  |
| 33 | Hydrant, Rem | Ea | 25 |  |  |
| 34 | Gate Well,Rem | Ea | 5 |  |  |
| 35 | Flowable Fill, Non-Structural | Cyd | 34 |  |  |
| 36 | Project Cleanup | LSUM | 1 |  |  |
| 37 | Fire Hydrant | Ea | 24 |  |  |
| 38 | Gate Valve and Box, 6 inch | Ea | 23 |  |  |
| 39 | Gate Valve and Box, 12 inch | Ea | 8 |  |  |
| 40 | Water Main, 6 inch, Tr Det G | Ft | 9045 |  |  |
| 41 | Water Main, 12 inch, Tr De G | Ft | 2677 |  |  |
| 42 | Water Serv | Ea | 131 |  |  |
| 43 | Water Serv, Long | Ea | 105 |  |  |
| 44 | Gate Box, Adj, Case 1 | Ea | 27 |  |  |
| 45 | Water main Tie-in | Ea | 27 |  |  |
| 46 | Pressure Test and Disinfect | Ea | 13 |  |  |
| 47 | Water Main Cross, 6 inch by 6 inch | Ea | 5 |  |  |
| 48 | Water Main, Tee, 6 inch by 6 inch | Ea | 3 |  |  |
| 49 | Water Main Bend, 45 Deg, 6 Inch | Ea | 22 |  |  |
| 50 | Water Main Bend, 22.5 Deg, 6 inch | Ea | 1 |  |  |
| 51 | Water Main Bend, 11.25 Deg, 6 inch | Ea | 2 |  |  |
| 52 | Water Main Tee, 8 inch by 6 inch | Ea | 3 |  |  |
| 53 | Water Main Reducer 12 inch by 6 inch | Ea | 1 |  |  |
| 54 | Water Main Cross, 6 inch by 8 inch | Ea | 2 |  |  |
| 55 | Water Main Bend, 11.25 Deg, 12 inch | Ea | 2 |  |  |
| 56 | Water Main Tee, 12 inch by 12 inch | Ea | 3 |  |  |
| 57 | Water Main Tee, 12 inch by 6 inch | Ea | 7 |  |  |
| 58 | Water Main Bend, 22.5 Deg, 12 inch | Ea | 2 |  |  |
| 59 | Water Main Tee, 16 inch by 12 inch | Ea | 1 |  |  |
| 60 | Sidewalk Ramp, Conc, 6 inch | Sft | 1657 |  |  |
| 61 | Detectable Warning Surface | Ft | 170 |  |  |
| 62 | Erosion Control, Gravel Access Approach | Ea | 3 |  |  |
| 63 | Exploratory Excavation | Ea | 1 |  |  |

| TOTAL BID | _________________ |
| --- | --- |

BID CONDITIONS

It is expressly understood and agreed that the total base bid as reflected on the attached Bidding Schedule is the basis for establishing the amount of the bid security on this bid and that this total base bid is not to be construed a Lump Sum Bid. It is further understood that quantities in the Bidding Schedule for unit price items are approximate only, and that payment of a contract will be made only on the actual quantities or work completed in place, measured on the basis defined in the General Provisions, Contract Specifications or other Contract Documents.

The undersigned has carefully checked the attached Bidding Schedule against the Contract Drawings and Specifications and other Contract Documents before preparing this Bid and accepts the said quantities to be substantially correct, both as to classification and amount, and as correctly listing the complete work to be done in accordance with the Contract Drawings, Specifications and other Contract Documents.

BID SECURITY

Accompanying this bid is a ________________ in the amount of five percent (5%) or ___________________ Dollars ($___________). The total amount of bid security is based on the total base bid of this Bid.

COMPLETION

If awarded a contract under this Bid, the undersigned agrees to start work at the site April 15, 2018.   The undersigned further agrees to complete the project by October 31, 2018.

LIQUIDATED DAMAGES

Liquidated damages of $500.00 per calendar day will be assessed for failure to meet any deadline, as noted in the Project Specifications.

BIDDER'S SIGNATURE:  Complete the applicable paragraph below.

I certify, under penalty of perjury, that I have the legal authorization to bind the firm hereunder, and that our firm is not debarred from doing business under the Federal Excluded Parties List System (epls.gov).

I, the Contractor or Contractor’s legally authorized signer, further certify compliance with the City of Battle Creek Ordinance Chapter 214, Discrimination Prohibited.  I further acknowledge and agree that the Contractor's violation of Chapter 214 shall be a material breach of this contract.  In addition, Contractor acknowledges and agrees that it shall be liable for any costs or expenses incurred by the City in obtaining from other sources, the work and services to be rendered or performed or the goods or properties to be furnished or delivered to the City under the contract as a result of a material breach in the Contract for violations of Chapter 214.

| (a) Corporation The bidder is a corporation organized and existing under the State of _______________________, which operates under the legal name of __________________________, and the full names of its officers are as follows: President: __________________________________ Secretary: __________________________________ Treasurer: __________________________________ Manager: __________________________________ (b) Co-Partnership The bidder is a co-partnership consisting of individual partners whose full names are as follows: _______________________ ______________________ ________________________ ______________________ ________________________ ______________________ ________________________ ______________________ (c) Individual The bidder is an individual whose full name is __________________ and, if operating under a trade name, said trade name is _________________________________. NAME: ________________________ ADDRESS: _____________________ CITY & STATE: __________________ | THIS BID OFFERED BY: SIGNATURE: NAME: TITLE: PHONE: FAX: EMAIL: (SEAL) Subscribed and sworn to before me this ____ day of ____________, 2018. ____________________________ Notary Public County of ____________________ Commission Expires: _________ |
| --- | --- |

# SECTION III - CONTRACTOR'S BID FORMS

THESE FORMS MUST BE RETURNED WITH THE BID

TABLE OF CONTENTS

CONTRACTOR'S BID BOND

CORPORATION CERTIFICATE

SUBCONTRACTOR AND DBE FORM

STATEMENT OF EXPERIENCE OF BIDDERS

CONTRACTOR'S BID BOND

KNOW ALL MEN BY THESE PRESENTS, That we, 			, (hereinafter called the "Principal"), and 		(hereinafter called the "Principal"), and 								 hereinafter called the  "Surety"), a corporation chartered and existing under the laws of the State of 				, with its principal offices in the City of 		 and authorized to do business in the State of Michigan, are held and firmly bound unto the City of Battle Creek (hereinafter called the "Owner"), in the full and just sum of 					 Dollars ($				) good and lawful money of the United States of America, to be paid upon demand of the Owner, to which payment well and truly to be made, the Principal and Surety bind themselves, their heirs, executors, administrators, and assigns, jointly and severally and firmly by these presents.

WHEREAS, the Principal is about to submit, or has submitted to the Owner, a Bid for furnishing all labor, materials, equipment and incidentals necessary to complete this contract.

WHEREAS, the Principal desires to file this bond in accordance with law, in lieu of a certified bidder's check otherwise required to accompany this Bid.

NOW, THEREFORE: The conditions of this obligation are such that if the Bid be accepted, the Principal shall, within ten (10) days after the date of receipt of a written notice of award of contract, execute a contract in accordance with the Bid and upon the terms, conditions and price(s) set forth therein, of the form and manner required by the Owner, and execute a sufficient and satisfactory contract performance bond payable to the Owner, and in an amount of One Hundred Percent (100%) of the total contract price in the form and with security satisfactory to said Owner, then this obligation to be void; otherwise to be and remain in full force and virtue in law; and the Surety shall, upon failure of the Principal to comply with any or all of the foregoing requirements within the time specified above, immediately pay to the aforesaid Owner, upon demand, the amount hereof in good and lawful money of the United States of America, not as a penalty but as liquidated damages.

IN TESTIMONY THEREOF, the Principal and Surety have caused these presents to be duly signed and sealed this 		 day of 						, 2018.

Principal

By:

(Seal)

Surety

By:

(Seal)

Countersigned:

CERTIFICATE TO BE EXECUTED

IF

CONTRACTOR IS A CORPORATION

I, 								, certify that I am the 										 of the Corporation named as Contractor hereinabove; that 								 who signed the foregoing Agreement on behalf of the Contractor was then the 								 of said Corporation; that said Agreement was duly signed for and in behalf of said Corporation by authority of its governing body and is within the scope of its corporate powers.

(Corporate Seal)

SUBCONTRACTOR AND DBE FORM – submit with bid

I.  	YOUR FIRM’S BACKGROUND:

Is your firm an MBE (at least 51% minority ownership)?  	_____YES  	_____NO

Is your firm a WBE (at least 51% woman ownership)?   	_____YES  	_____NO

Are you subcontracting any part of this project?		 	  _____YES  _____NO

II.  	SUBCONTRACTING INFORMATION:  If subcontracting any part of the project, the bidder/contractor expressly agrees that:

(1)	If awarded a contract as a result of this bid, the major subcontractors used in the prosecution of the work will be those listed below, and

(2)	The following list includes all subcontractors who will perform work representing approximately five percent (5%) or more of the Total Base Bid.

- The Bidder represents that the subcontractors listed below are financially responsible and are qualified to do the work required.

| SUBCONTRACTOR NAME | City/State | Trade or Commodity | MBE | WBE | Approximate dollar value |
| --- | --- | --- | --- | --- | --- |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | $____________________ |

III. DBE RECRUITMENT ACTIVITY LOG:  List the MBE’s and WBE’s that were approached about being a subcontractor for this job, but who are NOT listed above as a subcontractor.

| NAME OF FIRM APPROACHED, BUT NOT USED ON THIS PROJECT | City/State | Trade or Commodity | MBE | WBE | Reason not used on this project |
| --- | --- | --- | --- | --- | --- |
| ________________________________________ |  | ______________ | Y / N | Y / N | _______________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | _______________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | _______________________ |
| ________________________________________ |  | ______________ | Y / N | Y / N | _______________________ |

# SECTION IV - CONTRACTOR'S CONTRACT FORMS

THESE FORMS WILL BE REQUIRED FOR AWARD

CONTRACT FORM

PERFORMANCE BOND

LABOR AND MATERIAL BOND

CONTRACT FORM

CONTRACT NO. 2018-058B

2018 CITY OF BATTLE CREEK WATER MAIN PROJECT

THIS AGREEMENT, made and entered into this 				 day of 						, 2018, by and between 								 hereinafter called the "Contractor" and the City of Battle Creek, hereinafter called the "Owner.”

WITNESSETH: In consideration for the mutual covenants hereinafter stated, the parties agree for themselves, their personal representatives, successors, assigns as follows:

I. The Contractor promises and agrees:

A. To furnish all materials, construction water, equipment, tools, dewatering devices, skill and labor of every description necessary or reasonable incidental to carrying forth and completing in good, firm, substantial and workmanlike manner, the work specified, in strict conformity with the true intent of the NOTICE TO BIDDERS, SPECIAL INSTRUCTIONS, GENERAL INSTRUCTIONS, BID, SPECIAL CONDITIONS, GENERAL CONDITIONS, AGREEMENT, BONDS, GENERAL SPECIFICATIONS, and Project Specifications, and other contract documents and addenda thereto, which are hereby made a part hereof as fully and to the same effect as though they had been set forth at length herein.

B. To commence work under this contract on or before a date to be specified by the owner in a written Notice to Proceed and complete the project by the date specified in Bid.

C. Requirements for a specific trade or contract will generally be described in that portion of the specifications or drawings related to that trade or contract.  Such requirements may, however, be described in other sections of the Contract Documents. The Contractor will be held responsible for having carefully examined all drawings and read all requirements of the specifications and all Contract Documents to avoid omissions or duplications and to insure a complete job.

D. The Contractor must be fully informed about conditions relating to the construction of the project and the employment of labor thereon. Failure to do so will not relieve a successful bidder of his obligation to furnish all material and labor necessary to carry out the provisions of his contract.

E. Any claim by the Contractor of an inability to meet any requirement set forth in the Contract Documents, or that any requirement of these documents is impractical or unreasonable, will not be recognized, unless the claim was made at the time his Bid was submitted, and specific provision is made for such claim in the Agreement between Owner and Contractor (Bid and Agreement).

F.  Warranty:  Contractor shall remove and replace at no additional cost to the City any defects in workmanship or materials that may be apparent or may develop within a period of one (1) year from the date of final acceptance.

G. NON-DISCRIMINATION CLAUSE: The bidder agrees not to discriminate against any employee or applicant for employment, to be employed in the performance of such contract with respect to hire tenure, terms, conditions or privileges, of employment, or any matter directly or indirectly related to employment because of his or her actual or perceived race, color, religion, national origin, sex, age, height, weight, marital status, physical or mental disability, family status, sexual orientation, or gender identity. Breach of this covenant may be regarded as a material breach of the contract as provided for in Act 220 and Act 453 of the Public Acts of 1976, as amended, entitled "Michigan Handicapper's Civil Rights Act" and/or the "Michigan Elliott Larson Civil Rights Act" and/or City of Battle Creek Chapter 214 "Discrimination Prohibited" Ordinance. The bidder further agrees to require similar provisions from any subcontractors, or suppliers. The bidder agrees to comply with the Executive Order 11246 of September 24, 1965, entitled "Equal Employment Opportunity," as amended by Executive Order 11375 of October 13, 1967, as supplemented in Department of Labor regulations (41 CFR, Chapter 60).

II. The Owner promises and agrees:

- To pay the Contractor for said work when completed in accordance with the provisions of these contract documents, and for the contract sum of:

dollars ($						). Payment for work is subject to additions provided therein and for the authorized work complete in place and accepted by the Owner or its authorized representatives.

III. It is further understood and agreed between the parties hereto as follows:

A. The said work is to be done in accordance with the laws of the State of Michigan to the entire satisfaction and approval of the Owner or its duly authorized representatives.

B. The decision of said Owner's authorized representative upon any questions connected with the execution of this Agreement or any failure or delay in the prosecution of the work by said Contractor shall be final and conclusive.

C.  If, at any time after the execution of the Agreement and the Bond for its faithful performance, the Owner shall deem the surety or sureties then upon said bond to be unsatisfactory or, if, for any reason said bond shall cease to be adequate security for the performance of the work, the Contractor shall, at his expense, within fifteen (15) calendar days after receipt of written notice from the Owner to do so, furnish an additional bond or bonds in such form and amount and with such surety or sureties as shall be satisfactory to the Owner. In such event, no further payment to the Contractor shall be deemed to be due under this Agreement until such new or additional security for the faithful performance of the work shall be furnished in a manner and form satisfactory to the Owner.

D.  VENUE:  Any party bringing a legal action or proceeding against any other party arising out of or relating to this Agreement or the transactions it contemplates shall bring the legal action or proceeding:

(i) in the United States District Court for the Western District of Michigan; or

(ii) in any court of the State of Michigan sitting in Calhoun County, if there is no federal subject matter jurisdiction.

E. GOVERNING LAW:  This agreement shall be enforced under the laws of the State of Michigan.  Contractor must comply with all applicable federal, state, county, and City laws, ordinances, and regulations.  Contractor shall ensure payment of all taxes, licenses, permits, and other expenses of any nature associated with the provision of services herein.  Contractor shall maintain in current status all Federal, State and Local licenses and permits required for the operation of the business conducted by the Contractor.

IN WITNESS WHEREOF, the said parties have hereunto set their hands and affixed their seals, the day and year first above written.

STATE OF MICHIGAN)

) ss

COUNTY OF CALHOUN)

In the Presence of:

Notary Public

CONTRACT FORM APPROVED BY:

City Attorney

SIGNED, SEALED, AND

EXECUTED BY CONTRACTOR:

I certify, under penalty of perjury, that I have the legal authorization to bind the firm hereunder, and that our firm is not debarred from doing business under the Federal Excluded Parties List System (epls.gov):

By:

Title:

SIGNED, SEALED, & EXECUTED

BY CITY OF BATTLE CREEK

City Manager

PERFORMANCE BOND

KNOW  ALL  MEN  BY  THESE  PRESENTS,  that 										, as Principal, and									, as Surety, are held and firmly bound unto the City of Battle Creek in the  full  and just  sum of 													Dollars ($					) lawful money of the United States of America for the payment of which sum of money well and truly to be made, we bind ourselves, heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS, the Principal has entered into a certain written contract dated the				 day of 					, 20		 for the 						 complete, as described in the foregoing Bid and Agreement.

NOW THE CONDITIONS OF THIS OBLIGATION ARE SUCH, that if the said Principal shall in all respects well and truly keep and perform the said contract, and shall pay all sums of money due or to become due, for any labor, materials, apparatus, fixtures or equipment furnished for the purpose of constructing the work provided in said contract, and shall defend, indemnify and save harmless said City of Battle Creek against any liens, encumbrances, damages, claims, demands, expenses, costs and charges of every kind except as otherwise provided in said specifications and other Contract Documents arising out of or in relation to the performance of said work and the provisions of said contract, and shall remove and replace any defects in workmanship or materials which may be apparent or may develop within a period of one (1) year from the date of final acceptance, then this obligation shall be null and void; otherwise it shall remain in full force and effect.

And the said Surety, for value received, hereby stipulates and agreed that no change, extension of time, alteration or addition to the terms of the contract or to work to be performed thereunder or the specifications accompanying the same shall in any wise affect its obligation on this bond, and it does hereby waive notice of any such change, extension of time, alteration or addition to the terms of the Agreement or to the work or to the specifications.

IN WITNESS WHEREOF, we have hereunto set our hands and seals this 		 day of 				, 2018.

| PRINCIPAL ATTEST: |  |
| --- | --- |
| Principal Business Name Address City, State, Zip | Principal Secretary Signature & Seal Principal Secretary Printed Name Witness of Principal |
| SURETY ATTEST: |  |
| Surety Business Name Address City, State, Zip | BY: Attorney-in-Fact Signature & Seal Attorney-in-Fact Printed Name |

LABOR AND MATERIALS BOND

KNOW ALL MEN BY THESE PRESENT, that we, the undersigned, ____________________, hereinafter called the "Principal,” and _________________________, a corporation organized and existing under the laws of the State of ______________, having its principal office at ________________________, hereinafter called the "Surety,” are held and firmly bound unto the City of Battle Creek, hereinafter called the "Owner,” for use of any and every person, co-partnership, association or corporation interested in the full and just sum of ___________________________Dollars ($__________), lawful money of the United States of America, to be paid to the said obligees or its or their assigns, to which payment well and truly to be made we bind ourselves, our heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents. Sealed with our respective seals and dated this ____ day of ____________, 2018.

WHEREAS, the above bounded _________________________, Principal, has entered into a contract with the City of Battle Creek.

Dated the ______ day of ________________, 2018, for the ____________________________.

NOW, THEREFORE, THE CONDITION OF THIS CONDITION IS SUCH, that if the above bounded Principal shall and will promptly pay or cause to be paid all sums of money which may be due any person, co-partnership, association or corporation for all material furnished and labor supplied or performed in the prosecution of the work, whether or not the said material or labor enter into and become component parts of the work or improvement contemplated, then this obligation to be void; otherwise to remain in full force and effect.

The Principal and Surety further jointly and severally agree with the obligee herein that every person, co-partnership, association or corporation who, whether as subcontractor or otherwise, has furnished material or supplied or performed labor in the prosecution of the work as above provided and who has not been paid therefore may sue in assumption on this bond in the name of the Owner for his, their, or its use, prosecute the same to final judgment for such sum or sums as may be justly due him, them, or it, and have execution thereon, provided, however, that the Owner shall not be liable for payment of any costs or expenses of any such suit.

IT IS FURTHER AGREED, that any alterations which may be made in the terms of the contract or in the work to be done or materials to be furnished or labor to be supplied or performed under it or the giving by the Owner or any extension of time for the performance of the contract or any other forbearance on the part of either the Owner or the Principal to the other, shall not in any way release the Principal and Surety or Sureties or either or any of them their heirs, executors, administrators, successors or assigns, from their liability hereunder, notice to the Surety or Sureties of any such alteration, extension or forbearance being hereby waived.

IN WITNESS WHEREOF, the said Principal and Surety have duly executed this bond under the seal and day and year first above written.

ATTEST:

Principal

BY:

(Seal)

Surety

ATTEST		BY:

Attorney-in-Fact

(SEAL)

# SECTION V - SPECIAL CONDITIONS

1. 	Supplementary Definitions:  The following additional definitions supplement the definitions included in the General Contract Specifications BC 19-08, Paragraph I-1 of the General Conditions of Contract:

(a)  "Owner" or "City of Battle Creek" or "City" shall mean the City of Battle Creek, MI, acting through the City Commission or any other board official, or officials to which or whom the power belonging to the Commission shall, by virtue of any act or acts thereafter passed are held to appertain.

(b) "Engineer" shall mean the City Engineer, or other persons designated by the City acting directly or through authorized agents.

2. 	Contract Drawings:  The drawings applicable to the work to be performed under this contract and which are referred to in this documents as the plans or as the contract drawings.

3. 	Photographs:  Construction photographs will not be required.

The location of existing piping and underground utilities, such as gas mains, electric duct lines, etc., as shown on the Contract Drawings has been determined from the best available information by actual surveys or furnished and taken from the records of the parent utility companies and drawings of the existing facilities.  However, the City does not assume responsibility that during construction utilities other than those shown may be different from the locations designated on the Contract Drawings.

At locations where detailed positions of these facilities become necessary to the new construction, the Contractor shall, at his own expense, furnish all labor and tools to either verify and substantiate the record drawing locations or definitely establish the position of the facilities.

4.	Insurance:  The Public Liability and Property Damage Insurance shall also include the following coverages:

Contractor's Protection (Subcontractors to the Contractor)

Products - Completed Operations.

5. 	Responsibility to the Public:  Before every construction operation that will substantially affect area residents and businesses adjacent to the project site (such as business driveway closures, mailbox relocation, etc.) the Contractor will attempt to notify those residents and businesses affected.  Notification may be verbal or by door hanger notices.  The City will provide preprinted door hanger material to carry the Contractor's message.   The responsibility for filling out the door hangers and distributing them rests with the Contractor.  Payment for this work is included in the payments for other items of work.

6.	 Accident Reports From Contractor:  The Contractor shall furnish to the City copies of the reports of all accidents occurring at the construction sites from beginning to completion of his work under this contract.

7. 	Location and Marking Underground Utilities:  The Contractor shall be responsible for contacting the Calhoun County Construction and Utilities Association (MISS DIG) 72 hours prior to starting construction for the location and marking of all underground utilities.

8.	Paving Operations-Last Loads:  It is the responsibility of the Contractor to determine the amount of material used to complete a specific project or to conclude a day's construction.  Therefore, the City will not pay for an entire truck load if not used to complete the work.

A method of measurement mutually agreeable to both the City and the Contract to determine the portion of the truckload placed will be determined before paving operations begin.

9.	Street Sweeping:  If the Contractor requests the City to sweep a street under construction, the Contractor shall give to the Engineer a written request for such service at least 24 hours in advance.  Billing for this service will be handled by the City's Public Service Department.  VACUUM SWEEPING ONLY SHALL BE PERFORMED ON THIS PROJECT.

10.	Dust Control:  The contractor shall furnish, install and use appropriate measures to control dust at the construction site at all times.  If appropriate measures are not taken in the opinion of the engineer, the city may use its own force to control the dust and all charges for doing so will be charged to the contractor.

11.	Driveway Access:  Special consideration shall be made by project Contractor to minimize the obstruction of driveways along the project.  The Contractor shall maintain traffic, both in and out, during the entire project.

12.	Traffic Signs:  Contractor shall remove and stockpile all existing traffic signs at the direction of the engineer in the field.  (Incidental to the project.)

13.	Restoration:  The contractor shall grade all disturbed areas around new sidewalk within 48 hours of placement of same.

14.	Butt-Joints:  The Contractor will be required to construct a butt joint at all construction paving limits adjoining existing roads.  This will include sawcutting the joint to expose a minimum of 1.5-inch vertical face the entire width of the adjoining existing street.  This shall also include all intersections along the construction limits.  The sawcutting will be incidental to the project.

15.	Property Corners:  	All property irons, monuments, benchmarks, section and quarter section monuments that are removed or disturbed during construction shall be replaced by a Registered Land Surveyor, and documented on all drawings.  This shall be the responsibility of the Contractor and the cost considered included in Project Cleanup.

16.	Soil Erosion and Sedimentation Control:  All permits required shall be taken out by the Owner.  Any work and materials determined by the Engineer to	be required, that are not pay items in the contract, shall be provided by the Contractor according to MDOT specification 2.13.03 and be incidental to the total project bid.

17.	Test Boring: Test borings shall be provided by the Owner for Contractor's reference.  Owner makes no guarantee of accuracy or variations of soil changes or ground water conditions between boring locations.  Pavement thickness may also vary between boring locations.

18.	Curb and Gutter Construction: The contractor shall allow all new curb and gutter construction 48 hours of curing time prior to placing bituminous mixture against this new curb and gutter.  Also, the contractor will not be allowed to place any bituminous mixture on a given street, prior to the placement of all concrete curb and gutter marked for replacement.

- CONTRACTOR STORM WATER REQUIREMENTS.  The City of Battle Creek has a storm sewer system that is separate from its sanitary system.  Storm water from the city’s system drains directly to local waterways without typically being cleaned.  The City of Battle Creek is subject to the requirements of the Phase II Storm Water Regulations (the “Phase II Regulations”), 33 USC 1251, et seq., published by the United States Environmental Protection Agency (“EPA”) in the Federal Register on December 8, 1999.  One of the requirements is to ensure that contractors performing work for the city be trained in illicit discharges and pollution prevention and good housekeeping.  The following are the items each employee performing work for the City of Battle Creek must be trained on by his/her employer prior to work commencing:

General Requirements:

  - Block or add best management practices to storm drains in all construction or project areas prior to any work commencing.

  - A Soil Erosion and Sedimentation Control (SESC) permit is required for all sites within 500 feet of a lake, stream, or county drain; or if a site disturbs more than one acre of land.  Any sedimentation and erosion control practices should be well defined and all expectations should be clarified in all projects.

  - Clean or rinse all equipment in areas with a secure rinse pad or where wash water will not runoff into storm drains or surface waters.

  - Inspect equipment daily and repair any leaks. Use drip pans or absorbent materials to contain leaks until repairs are made.

  - Implement spill control and clean-up practices for leaks and spills from fueling, oil, or use of hazardous materials. Never allow a spill to enter the storm drain system.

  - Use the least hazardous material available for all projects. When the use of hazardous materials is necessary, ensure proper use, storage, and disposal of these materials.

  - Protect and maintain as much natural vegetation as possible during the project by phasing the project.

  - Properly dispose of all debris and excavated soil material – do not place near storm drains, rivers, streams, wetlands, or any environmentally sensitive area.

  - Minimize water use and control all storm water discharge where possible.

- Schedule activities for dry weather.

Illicit Discharges – all illicit discharges and illicit connections:

- Illicit discharges means any discharge to, or seepage into, a separate storm sewer that is not composed entirely of storm water or uncontaminated groundwater.  Illicit discharges include non-storm water discharges through pipes or other physical connections; the dumping of motor vehicle fluids, household hazardous wastes, domestic animal wastes, or leaf litter; the collection and intentional dumping of grass clippings or leaf litter; or unauthorized discharges of sewage, industrial waste, restaurant wastes, or any other non-storm water waste directly into a separate storm sewer.

- Illicit connection means a physical connection to the MS4 that 1) primarily conveys illicit discharges into the MS4, or 2) is not authorized or permitted by the local authority.

Bridge and Stream Crossing:

- Use suspended netting or tarps to capture paint, rust, paint-removing agents, or other materials to prevent discharge of materials to surface waters.

Paved Road and ng Lot Maintenance:

- Properly manage concrete slurry produced from diamond grinding, concrete sawing, or drilling activities using as little water as possible. Cover storm drains completely with filter fabric or plastic during the activity and contain the slurry using straw bales, sandbags, or gravel dams around the storm drains. Slurry management for diamond grinding can often be handled on site, such as reusing the solids from the grinding process while the water is infiltrated in the road right-of-way. For sawing and drilling activities, prevent wastewater from entering storm drains and surface waters by directing it to vegetated areas or vacuuming it for proper disposal.

- Do not use coal tar emulsions to seal asphalt surfaces.

Managing Vegetated Properties:

- Sweep grass clippings and leaves onto turf areas.  Do not allow clippings or leaves to go into the City’s municipal separate storm sewer system (MS4).

- The Manufactured Fertilizer Ordinance, Ordinance 13-07 – Chapter 650, must be adhered to should any project properties be fertilized.

# SECTION VI - SPECIAL PROVISIONS

NOTICE TO BIDDERS	23

PROGRESS CLAUSE	24

WATER MAIN	25

WATER MAIN APPROVED CONSTUCTION MATERIALS & PRODUCTS	36

EXPLORATORY EXCAVATION	38

HOT MIX ASPHALT BASE CRUSHING AND SHAPING, MODIFIED	39

HOT MIX ASPHALT (HMA) APPLICATION ESTIMATE	40

SIDEWALK, REM, MODIFIED	41

TURF ESTABLISHMENT, SPECIAL	42

DUST CONTROL	43

MAINTAINING LOCAL TRAFFIC	44

LEGAL RELATIONS AND RESPONSIBILITY TO THE PUBLIC	45

UTILITY COORDINATION	46

CITY OF BATTLE CREEK, MICHIGAN
DEPARTMENT OF PUBLIC WORKS
DIVISION OF ENGINEERING

## NOTICE TO BIDDERS

All work completed within The City of Battle Creek shall be done in accordance with the 2012 Standard Specifications for Construction of the Michigan Department of Transportation and the following Special Provisions and Supplemental Specifications as included herein.  The 2012 Standard Specifications for Construction of the Michigan Department of Transportation shall govern all technical specifications of this contract.

PROGRESS CLAUSE:  Work can start April 15th 2018.  This shall be the date designated as the starting date in the Detailed Progress Schedule.  In no case, shall any work be commenced prior to receipt of formal notice of award by the department.

- Due to the amount of residences impacted and extent of the project area the project shall be phased so that no more than 30+00 STA in total are pulverized and remain as such at one time.

Roads shall be adjacent

- Pressure Test and Disinfect shall be paid per street.

- Services and misc. concrete work shall be finished and the base course of HMA placed prior to the start of the next phase. Construction traffic shall be kept to a minimum over the base course.

- At no time shall the street sit idle for more than two (2) weeks after pavement has been removed.

- It is the contractor’s responsibility to uphold this schedule to assure residents and businesses are not inconvenienced for long durations.

The entire project shall be completed on October 31st 2018

Alternate advanced schedules will be considered by the Engineer upon review of proposed manpower and equipment of the contractor.

The selected bidder for the work covered by this proposal will be required to participate in a pre-construction meeting to work out a detailed progress schedule.  The schedule for this meeting will be set within one week after the approved bidder is determined.

The City of Battle Creek will arrange the time and place for the meeting.

Tjm 02/2018

SPECIAL PROVISION

FOR

## WATER MAIN

1 of 13

CEF/City of Battle Creek	                                                                                      December 2018

- GENERAL

1	Description

This work shall consist of installing and placing into operation water mains, water services, valves, hydrants, fittings, and other appurtenances of the required class and the specified sizes; and shall include excavation and backfilling. The Contractor shall furnish all labor, equipment and materials necessary to properly complete the work as shown on drawings and as specified herein.

All work and materials shall be in accordance to the requirements per Section 823 of the 2012 Standard Specifications for Construction by the Michigan Department of Transportation.

- CONSTRUCTION MATERIALS AND PRODUCTS

  - Shop Drawings

    - Shop drawings and manufacturers detailed literature shall be submitted to the Engineer for approval before any work may begin. These drawings shall detail the thrust restraint design for all fittings and pipe. Restraint shall be restraint joint pipe mechanism based on "Thrust Restraint Design for Ductile Iron" Sixth Edition 2006 as published by the Ductile Iron Pipe Research Association. Thrust blocks shall not be considered for calculating restraint design. The design shall be based on 150 psi or two times the working pressure, whichever is greater.

  - Pipe and Fitting Identification

- Each pipe, fitting or special section shall have plainly and permanently marked thereon:

    - Pipe class.

    - Thickness class.

    - Manufacturer's name or trademark.

    - On bends, the angle turned thereby.

    - Identification of specials to show proper location in line.

    - On beveled pipe, amount of bevel and point of maximum bevel.

    - Each end of each bevel end pipe, fitting, or special shall be marked with a stripe of paint, approximately 1½ inches wide and 2 feet long applied along the top centerline.

    - The Contractor shall be responsible for the handling and storing of all materials per manufacturer’s recommendations and to prevent deterioration and contamination from exposure to the weather and other conditions.

    - All damaged parts upon delivery or from storage shall be replaced at no cost to the owner.

  - Ductile Iron Pipe

- AWWA C151 minimum thickness Class 52 Pipe, cement – mortar lined and bituminous coated inside and outside in accordance with AWWA C104.

- Joints:

  - Slip-on compression type joint or mechanical joint meeting AWWA C111

  - Rubber gaskets shall conform to ANSI A21.11, AWWA C111, and AWWA C115

- Fittings:

  - Full Body meeting  AWWA C110

  - Compact meeting AWWA C153

  - All fittings to have mechanical joints meeting AWWA C111 and restrained.

See Appendix A, City of Battle Creek Approved Material Listing for joint restraints, ductile iron pipe, and pipe fittings.

  - Polyvinyl Chloride (PVC) Pipe

    - AWWA C900 DR18 PVC pressure pipe water main shall be manufactured from compounds conforming to PVC cell classification of 12454 as defined in ASTM D1784.  Pipe shall be blue in color and carries approval of ANSI/NSF Standard 61.  PVC pressure pipe will only be allowed up to 12 inches in diameter.

    - Joints

      - Slip-on compression type joint shall conform to ASTM F477 and ASTM 3139

      - Restrained joints shall utilize either JM Eagle Eagle Loc 900™ restrained joint system or Northern American Certa-Lok™ restrained joint system or approved equal.

    - Fittings

      - Full Body meeting  AWWA C110

      - Compact meeting AWWA C153

      - All fittings to have mechanical joints meeting AWWA C111 and restrained.

See Appendix A, City of Battle Creek Approved Material Listing for joint restraints, PVC pipe, and pipe fittings, and saddles.  Saddles shall be required on all Water Services connections to PVC pipe.

5	Valves and Boxes.

Resilient Wedge Gate Valves.

Required on 4” mains to 12” mains, or as directed by the Engineer.

      - All gate valves shall conform to the latest revision of AWWA Standard C509 or C515 covering resilient seated gate valves.  Valves shall be rated 250 psi.  All ferrous components shall be ductile iron.

      - Gate valves shall have an unobstructed waterway equal to or greater than the full nominal diameter of the valve.

      - The valves shall be non-rising stem, opening by turning stem Left (counter clockwise) and provided with a 2” square operating nut with the word Open and an arrow cast in metal to indicate the direction to open. Operating nut shall be constructed of ductile iron and shall have four flats at the stem connection.

      - The wedge shall be of ductile iron completely encapsulated with rubber. The wedge shall be symmetrical and seal equally well with flow in either direction.

      - The sealing rubber shall be permanently bonded to the cast iron wedge to meet ASTM tests for rubber metal bond ASTM D429.

      - Valves shall be supplied with O-ring seats at all joints. No flat gaskets allowed.

      - Stems shall be cast bronze with integral collars in full compliance with AWWA. The stem stuffing box shall be Oo-ring seal type with 2 O-rings located above the thrust collar and 1 O-ring below. The 2 O-rings above the collar shall be replaceable with the valve fully open and at its full working pressure.

      - There shall be 2 low torque thrust bearings located above and below the thrust collar.  The stem nut shall be independent of the wedge and shall be made of solid bronze. There shall be a smooth, unobstructed waterway free of all pockets, cavities and depressions in the seat area.

      - The body and bonnet shall be coated with fusion bonded epoxy both interior and exterior, complying with AWWA C550 and be NSF 61 approved. Each valve shall have the manufacturers’ name, pressure rating and the year manufactured, cast on the body.

See Appendix A, City of Battle Creek Approved Material Listing for resilient wedge gate valves.

    - Butterfly Valves.

Required on 16” mains or larger, or as directed by Engineer.

      - Butterfly valves shall comply with the latest revision of AWWA Standard C-504 Class 150B.

      - Butterfly valves shall be built to withstand a 150 psi working pressure.

      - Butterfly valve bodies shall be cast iron ASTM A126 Class B with mechanical joint ends complete with accessories (rubber, bolts, and glands).

      - Butterfly valve discs shall be ductile iron ASTM A536 Grade 65-45-12. All internal cast iron parts exposed to flowing water shall be coated with black asphaltic.

      - Butterfly valve body seating surface shall be stainless steel ASTM A276, Type 304. The mating seating shall be natural rubber or "Buna N Rubber" meeting the requirements of ASTM D2000. Seating shall be a 360 degree resilient seat fully field adjustable and field replaceable without valve disassembly.

      - Butterfly valve shafts shall be single solid stainless steel ASTM 276, Type 304. The shaft and disc shall be connected by means of O-ring sealed tapper pin held in place by a self-locking nut. The disc shall be held in the center of the valve by factory set thrust rings or collars. Shaft seals shall be of O-ring type or V-type packing.

      - Installation is for buried service. The valve shall be key operated with a 2" square operating nut open left (counter clockwise) and shall be located on the main side nearest to the edge of road or curb.

See Appendix A, City of Battle Creek Approved Material Listing for approved product listing for butterfly valves.

    - Valve Boxes.

All buried valves shall be provided with valve boxes. Valve boxes shall be cast iron, 2-piece with screw type extension sleeve adjustment and suitable for the depth of cover required by the drawings. Valve box shafts shall be 5-1/4 inches in diameter and shall have a minimum thickness at any point of 3/16 inch.  Valve box bases shall encapsulate the entire valve stem assembly, but not rest directly on the valve.  Covers shall be of a round plug type suitable for easy removal, and shall have cast thereon the word “WATER.”

      - All parts of valve boxes, bases and covers shall be coated by dipping in hot asphalt varnish.

See Appendix A, City of Battle Creek Approved Material Listing for approved product listing for valve box castings.

    - Service boxes.

Service boxes for 1 inch curb stops shall be two-piece 6500 Series Tyler Union 95-E which has a maximum height of 64 inches.  Services deeper than 64 inches must utilize one of the following  extensions:Tyler 151, 152, 153, or 154.

Service box for 2 inch curb stop shall be cast iron, 2-piece with screw type extension sleeve adjustment and suitable for the depth of cover required by the drawings. Valve box shafts shall be 5-1/4 inches in diameter and shall have a minimum thickness at any point of 3/16 inch.  Valve box bases shall encapsulate the entire curb stop assembly, but not rest directly on the curb stop.  Covers shall be of a round plug type suitable for easy removal, and shall have cast thereon the word “WATER.”

1 inch services shall be installed with a “Vadle Curb Box Lock” as per the manufactures recommendation and be included in the cost of other items.

See Appendix A, City of Battle Creek Approved Material Listing for approved product listing for valve box castings.

6	Fire Hydrant Assemblies.

- Hydrants shall conform to AWWA C502, as amended to date. All hydrants shall be “breakable” or “traffic” design, with replaceable sections or components of the barrel and stem.

- Hydrants shall have a compression type shut-off, opening against the pressure and which will remain closed in the event of accident, damage or breaking of the hydrant barrel.

- Hydrants are to have a minimum 5¼ inch valve opening with a 6 inch mechanical joint inlet and a 6 inch mechanical joint auxiliary gate valve between the water main and the hydrant.  Auxiliary gate valves shall be provided with a valve box.

- Hydrants shall be provided with two or more drain outlets, which are part of the main valve mechanism. The drain outlets are to be tapped and the drain plugs are to be threaded brass and installed at the time of delivery.  Removal of drain plugs shall be done by the Contractor prior to backfill unless groundwater is encountered or the Engineer directs otherwise.  Where necessary for drainage, aggregate meeting the requirements for MDOT Class 4G, 34R, or 34G as specified in Section 902 of the MDOT 2012 Standard Specifications for Construction, shall be placed at the base of the hydrant.

- Hydrants shall have O-ring packing.

- Hydrants, including tops and nozzle caps, shall be painted chrome yellow.

- Hydrants shall open left (counter-clockwise).  Hydrants shall have two standard 2½ inch hose nozzles and one 4½ inch pumper nozzle with National Standard Fire Hose threads and shall be equipped with caps, cap gaskets and chains.

- Operating nuts are to be pentagon in shape, measuring 1½ inches from flat to point. Height of the nut shall be at least 1 inch.

- Hydrants shall be designed so that the direction of the nozzles can be reoriented without digging up the assembly.

- Hydrants shall be designed so that an extension to the barrel can be added above ground without excavation.  Extensions shall be available in 6 inch increments.

- Hydrants shall be designed so that no excavation is needed to remove the main valve and movable parts of the drain valve.

- The bronze valve seat shall be threaded into a bronze drain ring or shoe bushing to provide ease of removal of the valve and valve seat on any hydrant that requires removal of the valve seat to replace the valve.

See Appendix A, City of Battle Creek Approved Material Listing for approved product listing for valve box castings.

7	Water Service Connections.

  - Copper pipe service connections of 1 inch or 2 inch, shall be in accordance with ASTM Specification B88, or Federal Specification WW-T-799; "Type K", soft tempered copper or HDPE pipe in accordance with ASTM F876, F877, F2023, F2657, constructed per AWWA C 904, and meet ANSI/NSF Standard 61 &14.

  - Plastic service connections of 1 inch or 2 inch shall be SDR 9 in accordance with ASTM D2737, constructed per AWWA C 901, and meet ANSI/NSF Standard 61.  Pipe dimensions shall meet copper tubing size standards.

  - Corporation stops shall be bronze, AWWA C-800 Table 1 standard inlet with AWWA standard outlet for compression fitting.

  - Curb stops shall be bronze, AWWA C-800 standard for compression fittings.

  - Service clamps for 2 inch service connections shall be of the double strap type, ductile iron, with all stainless steel or galvanized parts, similar to Romac Style 202NU.

  - Fittings for copper water services shall be of the compression type. Soldered joints shall not be used where pipe is buried.

See Appendix A, City of Battle Creek Approved Material Listing for approved product listing for valve box castings.

8	Pipe location devices

- All buried PVC and HDPE piping to have an electrically conductive [14 gauge] tracer wire with HDPE jacket to locate the pipe from grade level.  All grade level connection points for the purpose of locating buried pipe to be identified and submitted to the municipality.

- Tracer wire to be secured to the PVC or HDPE pipe at [10 ft.] maximum intervals.

- Tracer wire intersections shall be electrically isolated from ground and continuity provide per manufacture’s recommendation.

- Subsurface waterproof connectors specifically designed for buried service to be used.

9	Manhole Covers.

Covers shall meet the requirements of MDOT “Q” cover and the City of Battle Creek’s Standard Water Main Detail sheet that includes the city logo and the words “WATER” imprinted into the casting.

10	Pipe Testing.

At the discretion of the Engineer, pipe shall be tested for conformity with AWWA and ASTM specifications. The Engineer may choose one pipe per 1,000 feet of construction. The entire costs of testing shall be the Contractor's responsibility, whether performed by an independent testing lab or as part of the manufacturer's quality control.

11	Disinfection Materials.

a.	High Test Calcium Hypochlorite (HTH, "Perchloren", "Maxochlor", "Pittchlor"). - Powder and water shall be mixed to form a 1 percent chlorine solution (10,000 ppm), pumping solution at a constant rate into the water main while bleeding off the water at the extreme end.

b.	Liquid Chlorine. - Liquid chlorine conforming to AWWA B-301 may be applied to the water main much the same way as the hypochlorite solution listed above.

c.	Chlorine Gas. - Chlorine gas shall not be used.

- Construction Methods

  - Scope of Work

This section consists of excavation and backfill; placement of pipe, fittings and appurtenances; and disinfection of the completed water system per Section 823 of MDOT 2012 Standard Specification for Construction and the following specifications. It is the Contractor's task to proceed with the construction as rapidly and as expeditiously as possible and to present the City with a complete, sound, and operable piping system.

- The city will notify customer of shutoffs outside the project limit, but necessary to complete the work.  The contractor will be required to notify residences within the project limits via door hangers that the city will provide, but contractor must complete the information for times and durations of shutoffs along with providing contact information for coordination of work.

- Contractor will be allowed to operate valves within the project limits and as designated by the Engineer until acceptance of the completed water main system.

- Salvaged material shall be made available to the City of Battle Creek at a designated location within the project limits or other location as agreed to in the Progress Meeting.  Written notification of the material’s availability shall be from the Contractor to the Project Engineer, at which the city will be given 14 days to remove the salvaged material after which it becomes the property of the Contractor.  Salvage material includes, but not limited to, hydrants, manhole castings, valves, boxes, and other appurtenances.

  - Trench Excavation.

Water pipe shall be laid according to Utility Trenches detail F or G, as shown on MDOT Standard Plans R-83-B unless otherwise noted. Pedestrian crossings shall be erected and maintained by the Contractor where designated by the Engineer. The Contractor shall provide access to homes, commercial, industrial, etc. establishments as soon as backfill is completed. Said access shall always be provided during periods when the Contractor is not performing construction operations.

No trench shall be left open and unattended when pipe work is not being executed within the trench unless under an emergency in which case the trench shall be closed by fencing, barricading, or other methods until the emergency is resolved.  In no case shall the trench be left open overnight or on a weekend or holiday.

Undercutting unstable soil conditions within the trench shall be per Section 402.03.A of the current MDOT Standard Specifications for Construction and as directed by the Engineer.

  - Dewatering.

Dewatering of trenches shall be included as part of the water main installation with no separate payment. Dewatering shall be performed as necessary and shall conform to Section 402 of the current MDOT Standard Specifications for Construction, with the following additional requirements.

    - The Contractor shall perform his dewatering operations whenever groundwater conditions create an unstable trench bottom. An unstable trench bottom is defined as "Conditions that prevent placement of pipes true to line and grade."

    - The method of dewatering will be subject to review by the Engineer.

    - The City will be responsible for temporary service of an individual water supply where these supplies are cut off due to lowering of the water table during construction. The Contractor shall not lower the water table unnecessarily.

    - All dewatering wells that have a bore hole diameter of two inches or more shall be plugged and abandoned by the following method or any method that has been approved in writing by the Michigan Department of Public Health, in accordance with the State of Michigan's "Mineral Well Act," Public Act 315 of 1969.

    - Once the casing and screen have been removed from the bore hole, an injector pipe shall be installed in the bore hole to the bottom of the gravel pack material. Neat cement or bentonite slurry shall be pumped through the injection pipe until the material is five feet above the gravel pack material or four feet below the existing gravel level. The remainder of the bore hole shall be plugged with native soil.

    - Any water removed from the trench or the water main shall be disposed of in such a way as not to damage property, create a public nuisance or a health problem.

  - Joint Restraint.

Follow approved shop drawings and manufacturer’s recommendations based on “Thrust Restraint Design for Ductile Iron” Sixth Edition 2006 as published by the Ductile Iron Pipe Research Association.  Thrust blocks may be incorporated into the restraint system, but will not be considered for calculating restraint design

  - Installation of Pipe and Fittings

Before installation, the pipe shall be inspected for defects and any section of pipe or fittings found to be defective, before or after lying, will be rejected and replaced with sound pipe without additional expense to the City.

Water pipe shall be laid according to Utility Trench Detail F or G, as specified, on MDOT Standard Plans R-83-B. The interior of the pipe and fittings shall be thoroughly cleaned of foreign matter before being lowered into the trench and shall be kept clean during laying operations by plugging the ends or by other approved methods. When work is not in progress, the open ends of the pipe and fittings shall be securely closed so that no trench water, earth, animals, or other substances will enter the pipes.

No pipe or fittings shall be placed in water or when the trench or weather conditions are unsuitable for work except by permission of the Engineer.

The full length of each section of pipe shall rest solely upon the pipe bed, with recesses provided to accommodate the bells and joints.

Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets, shall not exceed tolerances recommended by the pipe manufacturer. If the alignment requires deflections in excess of the manufacturer's recommendations, special bends or a sufficient number of shorter lengths of pipe shall be furnished to provide the angular deflection required. Frequent or abrupt changes in the slope of the pipe, even if necessary to follow the existing ground surface elevations, will not be permitted.

Pipe shall be placed with bell ends facing in the direction of laying, unless otherwise approved by the Engineer.

Pipe shall be placed with at least 10-foot horizontal clearance from existing sewers and shall have a minimum clearance of 18-inches, as measured from outside edges of pipes, when crossing sewers.

Jointing of the various pipe materials and types shall be made in accordance with the manufacturer's recommendations.

  - Cutting Pipe

Cutting pipe for inserting valves, fittings, etc. shall be performed in a neat and workmanlike manner, without damage to the pipe or lining, and so as to leave a smooth end at right angles to the axis of the pipe.

For cast iron and ductile iron pipe, cutting shall be performed with a power saw, or a roller or shear type cutter for pipe sizes up to 20 inches in diameter. When machine cutting is not available for cutting pipe 20 inches in diameter or larger, the electric arc cutting method will be permitted, using a carbon or steel rod. Only qualified and experienced workmen shall perform this work.

For asbestos-cement or PVC pipe, cutting shall be performed by power saw, hand saw, abrasive disks or with a special asbestos-cement or PVC cutting tool. All piping cutting tools must be of the true cutting variety. Under no circumstances is the pipe to be cut with a roller or shear type cutting tool.

  - Connections to Existing Water Mains

Connections shall be made with line pressure on or off according to the Plans or Proposal. Existing pipelines shall be adequately supported during the cutting operations and prior to placement of backfill. Thrust blocks shall be placed behind all connected fittings.

Prior to cutting existing pipelines, the surface of the existing pipe shall be thoroughly cleaned by wire brushing and scraping. When cut-in is made under pressure, the existing pipe surface shall be washed down with a 4 percent solution of chlorine prior to installing the cutting-in tee. All fittings, pipe, valves, etc. used in the connection that cannot be disinfected during normal water main chlorination shall be swabbed out with a 4 percent or stronger solution of chlorine, such as standard laundry bleach, during assembly. Care shall be exercised in order to prevent contamination of the existing water mains and failure to comply with this requirement will necessitate chlorination of the existing water mains at the Contractor's expense.

After the connection is made, the Contractor shall flush sufficient water through the connection to effect removal of the chlorine solution.

All valves will be turned to the open position at the final inspection.

  - Valve Boxes

The valve box shall not transmit shock or stress to the valve when the box cover is flush with the surface of the pavement or other such level as may be directed. The base section of the valve box shall be set two inches above the flanged bonnet joint of the valve and accurately centered on the valve operating nut.

9	Hydrants

Hydrants shall stand plumb and have hose nozzle parallel with the roadway, with the pumper nozzle facing the roadway.

Hydrants shall be installed in conformance with AWWA C-600 and AWWA M-17. Hydrants shall be set to the established grade, with the breakaway no more than 8 inches above the finished topsoil grade or as directed by the Engineer. Nozzles should be placed at least 20 inches above the finished topsoil grade. Hydrants set with elbow or hydrant tee shall be rotated 90 degrees to conform to the above specifications.

At least 3 feet of horizontal clearance shall be provided around each hydrant from any above ground obstacles such as utility poles, trees, signs, fencing, walls, etc.

Hydrants must be connected to the main with a 6-inch branch and controlled by an independent gate valve. In the case of relocated four-inch hydrants, four-inch valves shall be used. This Valve on Branch shall be located no less than 18 inches or greater than 36 inches from the hydrant unless otherwise shown on the plans. Each Valve on the branch shall be left open prior to pressure testing and disinfecting and shall be left open prior to final acceptance.

A drainage pit shall be placed on both sides of the bottom inlet at the drainage waste opening.  The pit shall be 2 feet radial from the waste opening, at least 90 degrees in width, and 3 feet deep.  The pit shall be completely filled with specified aggregate to an elevation 6 inches above the waste opening.

10	Water Service

All water services shall originate at and include the tap into the water main in the street with a corporation stop and terminate with the connection to the existing service with a curb stop and service box located within 7 feet outside of the property line. All services shall be tapped at the 2 o’clock or 10 o’clock positions. Services shall be installed at a depth of 5 feet below the final grade. Short services shall be installed by boring. Borings may be made by the "Augur" or "Missile" methods. Services installed under existing concrete or bituminous surfaces shall be installed by boring. Services installed under gravel surface may be by open trench or boring.

Where soil conditions in open trenches are not suitable for copper pipe, the pipe shall be embedded in Granular Material Class III and backfilled as specified.

All services shall be observed for leaks and disinfected (chlorinated) before they are covered.

Curb stops will be placed in such a way that when turned off the key position is parallel to the centerline of the right of way that the water line services.

11	Seasonal Suspension

In the event that hazardous or nuisance conditions arise during the winter from the previous construction season's water main work, and such conditions are not corrected by the Contractor, the City shall notify the Contractor through the Engineer, in writing, that a deficiency exists and the specific location thereof. The Contractor shall, immediately upon such notification, correct the defective condition to the satisfaction of the City. Should the Contractor not correct the defective condition promptly, the City may perform the required maintenance and deduct their incurred costs from the contract price.

If the Contractor so desires, and by prior written consent of the City, he may elect not to perform such inspections and/or maintenance, due to prohibitive travel distances or shortage of off season manpower. Should the Contractor desire to initiate this exception, the City may perform the winter inspections and maintenance itself and deduct his incurred costs from the contract price.

IV	Hydrostatic Testing

1	General

The Contractor shall pretest and be satisfied that all lines are ready for testing before requesting test inspection. The Contractor shall provide all necessary equipment and perform all work required in connection with the tests.

  - Hydrostatic Testing

The test shall conform to AWWA C-600 and Section 823.03 T. of the 2012 Standard Specifications for Construction by MDOT for all newly laid pipe and fittings.

V	Disinfection of the System

1    General

Disinfection shall be by chlorination and/or other methods as approved by the Engineer after pressure testing and flushing. The disinfection shall conform to the current AWWA C-651 standards.

2	Chlorination

All new water lines shall be chlorinated. The Contractor shall furnish all labor, equipment, and materials necessary for effective chlorination of the water mains.

3	Materials

    - High Test Calcium Hypochlorite (HTH, "Perchloren", "Maxochlor", "Pittchlor"). - Powder and water shall be mixed to form a 1 percent chlorine solution (10,000 ppm), pumping solution at a constant rate into the water main while bleeding off the water at the extreme end.

    - Liquid Chlorine. - Liquid chlorine conforming to AWWA B-301 may be applied to the water main much the same way as the hypochlorite solution listed above.

    - Chlorine Gas. - Chlorine gas shall not be used.

4	Method of Chlorination

The chlorination agent shall be applied at the beginning of the section adjacent to the feeder main and shall be injected through a corporation cock, hydrant or other connection, insuring treatment of the entire line. Water shall be fed slowly into the new lines with chlorine applied to produce a dosage of not less than 50 ppm. Mains previously filled shall be treated to a concentrated dosage at intervals along the line and retained for a period of not less than 12 hours. A chlorine residual of not less than 5 ppm shall be produced in all parts of the line. During chlorination, all new valves and accessories shall be operated.

After chlorination, the water shall be flushed from the line at its extremities until all of the heavily chlorinated water has been removed, leaving a residual chlorine content not greater than 1.0 ppm.

After the applicable retention period, heavily chlorinated water shall not remain in prolonged contact with the pipe. In order to prevent damage to the pipe lining or corrosion damage to the pipe itself, the heavily chlorinated water shall be flushed from the main until chlorine measurements show that the concentration in the main is no higher than that generally prevailing in the distribution system or is acceptable for domestic use.

The chlorine concentrations in the discharged chlorination water shall not exceed the limits imposed by the Michigan Department of Environmental Quality and other regulatory agencies. Chlorine concentrations in discharges that occur over a period of 160 minutes or less shall not exceed 0.5 milligrams per liter. Chlorine concentrations in discharges that occur over a period longer than 160 minutes shall not exceed 0.038 milligrams per liter.

The environment into which the chlorinated water is to be discharged shall be inspected. If there is any possibility that the chlorinated discharge will cause damage to the environment, then a neutralizing chemical shall be applied to the water to be wasted to neutralize thoroughly the chlorine residual remaining in the water. Where necessary, Federal, state and local regulatory agencies shall be contacted to determine special provisions for the disposal of heavily chlorinated water.

The Contractor shall collect water samples in sterile bottles containing sodium thiosulfate for bacteriological analysis from the end-most outlet of the pipeline. Two samples shall be taken 24 hours apart for each section of line tested. If both samples show safe results and meet the Safe Drinking Water Standards, the new pipeline may be placed in service. If, however, the results are unsafe, a repetition of the chlorine treatment is necessary. Samples will never be taken from hoses or fire hydrants. A suggested sampling tap is a corporation cock with a copper gooseneck assembly. The gooseneck assembly may be removed after use. At the option of the City, samples shall be taken during chlorination.

VI	Measurement and Payment

The complete work as measured for Water Main will be paid for at the contract unit prices for the following items (pay items). Each item includes supplying all necessary material, equipment, and labor.

Pay Item	Pay Unit

Hydrant, Rem	Each

Water Main, Rem	Foot

Water Main, __ inch, Cut and Plug	Each

Gate Well, Rem	Each

Water Service, Rem	Each

Fire Hydrant	Each

Gate Valve and Box, __inch	Each

Water Main, __inch, Tr Det __	Foot

Water Serv	Each

Water Serv, Long	Each

Water Serv, 2 inch	Foot

Gate Box, Adj, Case __	Each

Water Main Tie in	Each

Live Tap, __inch by __inch	Each

Pressure Test and Disinfect	Each

Water Main Tee, __inch by __inch	Each

Water Main Reducer, __inch by __inch	Each

Water Main Cross, __inch by __inch	Each

Water Main Bend, __Deg, __inch 	Each

    - General

The actual number of units of each unit price item of work actually performed may be more or less than the number stated in the Bidding Schedule of the Proposal, or included in the Contract, but no variation in the Contract unit price will be made on that account. Payment will be made only for the actual number of units incorporated in the work, or for the actual number of units of work performed, and at the Contract unit price for each such unit with measurement for payment made as defined in the following paragraphs. Measurement for payment of work done on a unit price basis will be as follows.

- Hydrant, Rem.  Removing Hydrants will be paid for on an each basis. All existing hydrants will remain the property of the City and will be salvaged

- Water Main, Rem.  Removing water main will be paid per foot of water main removed and will include all excavation needed and hauling from site.

- Water Main, Cut and Plug.  The unit price for water main, cut and plug includes the cost of cutting the existing water main, providing and placing the required plug and thrust blocks.

- Gate Well, Rem.  Removing gate wells will include complete removal of the water valve pit and all surrounding heavy, saturated material

- Water Service, Rem.  Removal of water service shall be from the corporation at the main to the right-of-way and will be paid for on an each basis.  Salvaging existing curb boxes for the city’s use shall also be included in this item

- Fire Hydrant.  Fire hydrants will be paid for on an each basis. The payment for fire hydrant assemblies includes the hydrant, main line by 6 inch tee, 6" resilient wedge valve and box, rodding, thrust restraint, up to 10'-6" of Class 52 cement lined ductile iron pipe, aggregate, hydrant extension kits and other accessories necessary to complete the installation to proper grade and specifications

- Gate Valve and Box, __ inch.  The unit prices Gate Valve and Box, of the types and sizes required, include the cost of providing and installing the valve and valve box, complete and ready for use.

- Water Main

  - Water Main, __inch, Tr Det __.  Water main, of the diameter, class, and trench detail specified, will be measured in place, by length in linear feet, from center to center of cross mains with no deductions in length for intermediate structures. Payment shall include any dewatering or trench bracing/sheeting necessary along with any necessary restraints. Excavation and backfill will not be measured separately but shall be included as a part of the item of water main furnished and installed.  Price shall include any necessary tracer wire.

- Water Services

  - Water Serv.  Includes the tap, corporation, saddle, curb stop, service box, tracer wire and service pipe from within 5’ of the ROW to the short side of the water main.

  - Water Serv, Long.  Includes the tap, corporation, saddle , curb stop, service box, tracer wire and service pipe from within 5’ of the ROW to the long side of the water main.

  - Water Serv, 2 inch.  Shall be in addition with the Water Serv pay item for placing service pipe and includes the saddle and attachment to the main.  Tap, corporation, curb stop, tracer wire and service box from within 5’ of the ROW will be included with the Water Serv pay item.

- Gate Box, Adj. Case__.  Case 1 refers to structures located in hard surfaced travel areas and unit price includes saw cutting, removing and replacing existing pavement, curb, or curb and gutter, and adjusting the water shutoff or gate box to final grade. Case 2 refers to structures located outside existing pavement, curb or curb and gutter and unit price includes restoring disturbed vegetated or sidewalk areas.

- Water Main Tie in.  Connection of a new water main to an existing water main will be paid on an each basis for each connection made as noted on the plans.  Payment includes all items necessary to complete the work including excavation and backfill, cutting and removing existing water main, all fittings, reducers, bends, and sleeves with restraint necessary to align new main with existing main.

- Live Tap, __inch by __inch.  The unit price for Live Tap, of the size required, includes the cost of providing and installing the valve, tapping sleeve, all necessary restraints, and valve box, complete and ready for use. This work includes the complete live tapping procedure.

- Pressure Test and Disinfect.  Pressure Test and Disinfect Water Main will be paid once per location approved by the engineer. If the main fails to pass the first pressure and disinfectant tests, further tests shall be made at the Contractor's expense. Payment for flushing and disposal of the disinfectant chlorinated water in accordance with environmental regulations is included in this item.

- Appurtenances.  Water main tees, reducers, crosses, bends and other appurtenances shown on plans but not listed as bid items will be included with the water main items.

SPECIAL PROVISION

FOR

## WATER MAIN APPROVED CONSTUCTION MATERIALS & PRODUCTS

34 of 2

CEF/City of Battle Creek	                                                                  December 2018

| # APPENDIX A |  |  |
| --- | --- | --- |
| # City of Battle Creek Approved Material Listing |  |  |
| Pipe and Fittings | American Cast Iron Pipe Company | Fastite Joint Pipe |
|  | Clow Water Systems Company | Tyton Joint Pipe |
|  | U.S.Pipe and Foundry Company | Tyton Joint Pipe |
|  | JM Eagle | Blue Brute C900 |
|  | North American Pipe | AWWA C900 |
| Joint Restraints | EBAA Iron, Inc. | Mega Lugs |
|  | Romagrip Industries | RomaGrip |
| Resilient Wedge Gate Valves MJ x MJ | American Flow Control | Series 2500 |
|  | Clow Water Systems Company | F6100 |
|  | East Jordan Iron Works | Flowmaster MJ x MJ |
|  | Mueller Industries | A-2360-20 |
| Resilient Wedge Tapping Valves | American Flow Control | 2500 Series |
|  | Clow Water Systems Company | F6114 |
|  | East Jordan Iron Works | Flowmaster MJ x Tapping |
|  | Mueller Industries | T-2360 |
| Resilient Wedge Cut In Valve | Clow Water Systems | F6111 |
|  | Muller Industries | C-2360 |
| Butterfly Valves | Clow Water Systems Company | 4500 Series |
|  | Golden Anderson | GA AWWA C504 Butterfly Valve |
|  | Pratt | Groundhog Butterfly Valve |
| Valve Box Castings | Tyler Union – USA only | 6850 Two piece 664-S (26T & 36B) |
|  | East Jordan Iron Works | 8555 Two piece 668-S |
| Service Box Castings | Tyler Union – USA only | 6500 Series, 95-E (30T & 39B) |
| Curb Box Lock | JRC Supplies Inc. | The Vadle Curb Box Lock |
| Fire Hydrant Assemblies | American Flow Control | American Darling B-62-B-5 “Snow Model” |
|  | East Jordan Iron Works | Watermaster 5BR250 |
| Repair Clamps | Romac | Various |
|  | Mueller | Various |
| Saddle-Double Strap x2” | Romac | 202NU |
|  | Mueller | DR A Series |
| Service Saddle Strap 1” | Romac | 101S |
|  | AY McDonald | 4835A |
| Macro 2 Bolt Coupling | Romac Only | Various |
| Sleeves | Star Domestic | Various |
|  | Tyler Union | Various |
|  | U.S.Pipe and Foundry Company | Various |
| Service Line Fittings | A.Y. McDonald | Various (Must be NSF Compliant) |
|  | Mueller | Various (Must be NSF Compliant) |

SPECIAL PROVISION

FOR

## EXPLORATORY EXCAVATION

CEF	1 OF 1	2-5-18

a.	Description.  This work consists of providing all labor, equipment, and materials necessary to expose an existing culvert, sewer, sump discharge or utility, and verifying the condition, size, material, elevation and alignment, and backfilling the trench.  Perform the work in accordance with section 205 of the Standard Specifications for Construction and the contract.  Locate utility crossings and service leads as a part of the work.  Exploratory work required for locating existing utilities will not be paid for separately unless specifically called out on the plans or if the Engineer gives the Contractor explicit permission in advance of the excavation.  The intent of this work is not to provide payment to the Contractor for locating each existing utility throughout the project.  The Contractor is responsible for “using reasonable care to establish the precise location of the underground facilities in advance of construction” (2013 PA 174 - MISS DIG Underground Facility Damage Prevention And Safety Act) as a part of the overall project contract.

b.	Materials.  Ensure if the excavation is located within the limits of pavement or within a 1 on 1 influence of pavement, backfill the trench with Class II granular material and compact to at least 95 percent of the maximum unit weight.  If the trench is located outside of the limits of pavement, excavated material from the trench may be used to backfill the trench and compacted to at least 95 percent of the maximum unit weight, unless otherwise directed by the Engineer.

c.	Construction.  Prior to the exploratory excavation the contractor will provide documentation of the estimated cost associated with the work for review by the engineer.  Perform the exploratory excavation to expose the culvert, sewer pipe, or other facility to verify the condition, size, material, elevation and alignment of the pipe or facility.  Perform all work in conformance with 2013 PA 174 - MISS DIG Underground Facility Damage Prevention And Safety Act.  Contact the MISS DIG System a minimum of 3 full business days (72 hours) prior to beginning trenching.  Backfill the exploratory trench only after the Engineer has approved it for backfilling.

Replace, repair or install the facility in accordance with other contract pay items and with 2013 PA 174 - MISS DIG Underground Facility Damage Prevention And Safety Act, as directed by the Engineer.

Existing pay items will be utilized to compensate the Contractor for work necessary to complete the Exploratory Excavation.

d.	Measurement and Payment.  The completed work, as described, will be measured and paid for at the contract unit price using the following pay item:

Pay Item	Pay Unit

Exploratory Excavation	Each

Exploratory Excavation payment includes backfilling the trench and compaction as directed by the Engineer.

The completed work for Exploratory Excavation will only be paid for in those locations called out on the plans or as required by the Engineer.  Multiple utility verifications may be included in one paid excavation if the utilities are close in proximity.

SPECIAL PROVISION

FOR

## HOT MIX ASPHALT BASE CRUSHING AND SHAPING, MODIFIED

CAD:TJM	1 of 1	APPR:CEF:03-03-17

a.	Description.  This work consists of providing all labor, equipment and materials necessary to construct an aggregate base from the existing hot mix asphalt (HMA) pavement and aggregate base course as shown on the plans or as directed by the Engineer.

b.	Materials.  Provide materials in accordance with sections 302 and 305 of the Standard Specifications for Construction.

c.	Construction.  Ensure all work is accomplished in accordance with section 305 of the Standard Specifications for Construction except as described herein. Excess crushed material may be used for aggregate base material and maintenance gravel directed by the Engineer.

Dispose of any excess or unsuitable material in accordance with subsection 205.03.P of the Standard Specifications for Construction

d.	Measurement and Payment.  The completed work, as described, will be measured and paid for at the contract unit price using the following pay item:

Pay Item	Pay Unit

HMA Base Crushing and Shaping, Modified	Square Yard

HMA Base Crushing and Shaping, Modified includes additional crushed material needed to achieve plan grade or the removal of excess and/or unsuitable material.

SPECIAL PROVISION

FOR

## HOT MIX ASPHALT (HMA) APPLICATION ESTIMATE

1 OF 1

tjm/City of Battle Creek									March, 2017

DESCRIPTION

This work shall be done in accordance with the requirements of Division 5 of the MDOT 2012 Standard Specifications for Construction except as herein specified.

MATERIALS

The HMA BASE, 13A shall have a yield of 165 pounds per square yard and placed in lifts with a maximum thickness of 1.5-inches.

The HMA TOP, 13A shall have a yield of 165 pounds per square yard and placed in lifts with a maximum thickness of 1.5-inches.

Hand Patching shall be HMA, 13A, shall have a yield of 165 pounds per square yard, and placed in lifts with a maximum thickness of 1.5-inches.

The Performance Grade asphalt binder range shall be 58-28 for the HMA, 13A.

The Hot Mix Asphalt Bond Coat material shall be per Section 501.03. The uniform rate of application shall be 0.05 to 0.15 gallons per square yard.

The minimum Average Wear Index (AWI) shall be 260 for top course only.

For this project the 13A HMA mixture the target air voids shall be reduced to 3.0%.

MEASUREMENT AND PAYMENT

Measurement and Payment shall be at the contract unit price per ton.

# SPECIAL PROVISION

FOR

## SIDEWALK, REM, MODIFIED

1 of 1

krt/City of Battle Creek								May 8, 2009

- DESCRIPTION

This work shall be per Section 204 of the MDOT 2012 Standard Specifications for Construction with the exception that the removal of driveways along with concrete sidewalks will be considered as part of this item.  In addition, the pavement of the driveways will be considered as one entity with no distinction of material type or thickness and will include integral flared, winged, or curbed sections where main line curb is transitioned into the drive opening.  Asphalt pavements with underlying materials of concrete, brick, stone, or other pavement composites will be considered as part of the entire driveway entity and removal will be directed by the Engineer within the project limits.  This item shall be paid one time only regardless of the types or thicknesses encountered.  This item shall also include full depth saw cutting of all edges where pavement is to remain.  Saw cutting will be consider part of this item and not be paid as an extra item.

Disposal of materials shall be per Section 204.03.B 205 of the MDOT 2012 Standard Specifications for Construction.

Main line concrete curb and gutter will be paid separately under the Curb and Gutter, Rem pay item.

- MEASUREMENT AND PAYMENT

The completed work as measured will be paid for at the contract unit price for the following contract items (pay items).  The price shall be payment in full for furnishing all necessary labor, equipment and materials.  No additional payment will be made for pavement depths that vary from those indicated.

Pay Item	Pay Unit

Sidewalk, Rem, Modified	  Square Yard

# SPECIAL PROVISION

FOR

## TURF ESTABLISHMENT, SPECIAL

ESC/City of BC								        December, 2016

- description

Turf Establishment, Special shall be per Section 816 of the 2012 Standard Specifications for Construction and will include placement of 3 inches topsoil, Chemical Fertilizer Nutrient-Class C, Seeding Mixture TUF, Mulch (straw), and Anchoring Mulch at the specified rates.

The salvaged topsoil material shall be free of rock and wood debris.  Visable rocks, roots, branches, and other debris will be removed by the Contractor and consider included with this item. When salvaged topsoil is not suitable or there is not a sufficient amount for establishment, it is the contractor’s responsibility to bring screened-topsoil as part of the pay-item.

Payment for watering turf will be not be paid separately, but considered included and necessary in this item to establish the turf once the seed has germinated.

A one-year period of establishment commencing at the completion of the initial planting season will be required for all grass.  A growing season is defined as the months of June, July and August. All grass shall be in a healthy growing condition at the start of the establishment period. The Engineer will inspect the grass at the end of the first growing season to determine if grass is unacceptable.  Unacceptable grass is defined as being dead, missing, unhealthy, or otherwise unsatisfactory at the time of inspection, or grass that was not planted in conformance with these specifications.  At the contractor’s cost, replacement grass shall be replanted after September 15 following the initial growing season or prior to May 10 of the following spring planting season.  This replacement grass shall remain the responsibility of the general contractor of the original contract with no additional payment.

The Contractor will also be responsible for preparing the topsoil a second time prior to the re-establishment of grass following the initial growing season in any unacceptable areas.  This will include complete removal of weeds, raking and leveling the prepared soil along with the removal of any rocks or roots.

- measurement and payment

Turf establishment will be paid up to 2 Ft on either side of sidewalk unless agreed upon by the engineer.  All work to prepare and place topsoil for the establishment of turf shall be paid at the appropriate contract unit prices for the following contract items (pay items):

Pay Item	Pay Unit

Turf Establishment, Special	Syd

SPECIAL PROVISION

FOR

## DUST CONTROL

1 of 1

dkb/City of Battle Creek								April, 2012

###### DESCRIPTION

The Contractor will be required to water down all areas of exposed road base to eliminate dust from the project per Section 107.15 of the 2012 MDOT Standard Specifications for Construction.  Dust control shall be done daily while work is performed or as directed by the Engineer.  The number of water applications will be determined daily as necessary to eliminate dust.  The Engineer will make the determination of the number of applications necessary.  The Dust Control item will be paid as one each per day water is applied to the exposed road base regardless to the frequency of water applications.

If the Contractor fails to apply a requested water application then the Contractor will be penalized the dust control unit price for that day’s dust control.  If the Contractor fails on three separate occasions, the City will have the option of hiring a separate independent contractor to provide the required applications.  The cost, which may exceed the dust control item unit contract cost, will be the responsibility of the General Contractor.

###### MEASUREMENT AND PAYMENT

The completed work as measured for items in this division will be paid for at the contract unit price(s) for the following contract items (pay items).  The price shall be payment in full for furnishing all labor, equipment and material and shall include:  furnishing and placing water, and all other work required for a complete job.

Pay Items				               Pay Unit

# Dust Control					   Each

SPECIAL PROVISIONS

FOR

## MAINTAINING LOCAL TRAFFIC

- DESCRIPTION

This item consists of supplying all labor and material required to maintain driveway access at all times to each driveway currently in use within the construction zone.  Part width driveway construction and in some cases, construction of temporary driveways next to the existing ones will be permitted.  Temporary approaches will be constructed from maintenance gravel or approved material.  This item shall also include placing maintenance gravel or approved material in the roadway, where it is necessary to provide access to resident/business driveways.  This item shall be paid on a lump sum basis.

- MEASUREMENT AND PAYMENT

The completed work as measured will be paid for at the contract unit price for the following contract items (pay items).  The price shall be payment in full for furnishing all necessary labor, equipment and materials.

Pay Item							Pay Unit

MAINTAINING LOCAL TRAFFIC	LSUM

NOTICE TO BIDDER

## LEGAL RELATIONS AND RESPONSIBILITY TO THE PUBLIC

krt/City of Battle Creek								August, 2006

##### DESCRIPTION

Before every construction operation that will substantially affect area residents and businesses adjacent to the project site, (such as driveway closures, mailbox relocation, etc.) the contractor will notify those residents and businesses affected.

Notification will be by door hanger notices.  The City will provide preprinted door hanger material to carry the Contractor’s message.  The responsibility for filling out the door hangers and distributing them will be the Contractor’s.  Payment for this work will not be paid for separately, but payment will be considered as having been included in the contract unit prices bid for other contract items.

## UTILITY COORDINATION

1of 1

The contractor shall cooperate and coordinate construction activities with the owners of utilities as stated in Section 104.07 of the 2012 MDOT Standard Specifications for Construction.  In addition, for the protection of underground utilities, the contractor shall follow the requirements in Section 107.12 of the 2012 MDOT Standard Specifications for Construction.  Contractor delay claims, resulting from a utility, will be determined based upon Section 109.03 of the 2012 MDOT Standard Specifications for Construction.

PUBLIC UTILITIES

The “Miss Dig” alert number is 800-482-7171.  The following Public Utilities have facilities located within the Right-of-Way:

AMERITECH / SBC				CONSUMER ENERGY CO.			SEMCO ENERGY

(telephone)						(electric)							(gas)

2919 Millcork					311 E. Michigan Ave.					15851 Helmer Road

Kalamazoo, MI 49001			Battle Creek, MI 49017				Battle Creek, MI 49015

269-384-4490					269-969-8595						269-420-7458

JEFF SAYLOR		 			MATTHEW KOEPKE				JULIE CONANT

COMCAST						CITY OF BATTLE CREEK			CITY OF BATTLE CREEK

(cable TV)						(Water Division)						(Sewer Division)

350 N. 22nd St.					150 S. Kendall St.					2000 W. River Rd.

Battle Creek, MI 49015			Battle Creek, MI 49015				Battle Creek, MI 49017

269-788-1150					269-966-3496						269-966-3513

JOE SCHOPT					MATTHEW MILLER				BRYAN CRAWFORD

CITY OF BATTLE CREEK

(Signs and Signals Division)

150 S. Kendall St.

Battle Creek, MI 49015

269-966-3527

JAMES TOBIAS

The owners of the existing service facilities that are within the grading or structure limits will move them, as shown on plans, to locations designated by the Engineer or will move them entirely from the Right-of-Way.  Owners of Public Utilities will not be required by the City to move additional poles or structure in order to facilitate the operation of construction equipment unless it is determined by the Engineer that such poles or structures constitute a hazard to the public or are extraordinarily dangerous to the Contractor’s operations.

Krt/1-22-18

# SECTION VII – PREVAILNG WAGES

General Decision Number: MI180001 01/05/2018  MI1

Superseded General Decision Number: MI20170001

State: Michigan

Construction Types: Highway (Highway, Airport & Bridge xxxxx

and Sewer/Incid. to Hwy.)

Counties: Michigan Statewide.

Note: Under Executive Order (EO) 13658, an hourly minimum wage

of $10.35 for calendar year 2018 applies to all contracts

subject to the Davis-Bacon Act for which the contract is awarded

(and any solicitation was issued) on or after January 1, 2015.

If this contract is covered by the EO, the contractor must pay

all workers in any classification listed on this wage

determination at least $10.35 per hour (or the applicable

wage rate listed on this wage determination, if it is higher)

for all hours spent performing on the contract in calendar

year 2018. The EO minimum wage rate will be adjusted annually.

Please note that this EO applies to the above-mentioned types

of contracts entered into by the federal government that are

subject to the Davis-Bacon Act itself, but it does not apply

to contracts subject only to the Davis-Bacon Related Acts,

including those set forth at 29 CFR 5.1(a)(2)-(60). Additional

information on contractor requirements and worker protections

under the EO is available at www.dol.gov/whd/govcontracts.

Modification Number     Publication Date

0             01/05/2018

CARP0004-004 06/01/2016

REMAINDER OF STATE

Rates          Fringes

CARPENTER ( Piledriver)..........$ 26.33            19.18

----------------------------------------------------------------

CARP0004-005 06/01/2016

LIVINGSTON (Townships of Brighton, Deerfield, Genoa, Hartland,

Oceola & Tyrone), MACOMB, MONROE, OAKLAND, SANILAC, ST. CLAIR

AND WAYNE COUNTIES

Rates          Fringes

CARPENTER (Piledriver)...........$ 29.47            25.94

----------------------------------------------------------------

ELEC0017-005 06/05/2017

STATEWIDE

Rates          Fringes

Line Construction

Groundman/Driver............$ 28.16       6.10+28.5%

Journeyman Signal Tech,

Communications Tech, Tower

Tech & Fiber Optic Splicers.$ 38.38       6.10+28.5%

Journeyman Specialist.......$ 44.14       6.10+28.5%

Operator A..................$ 32.45       6.10+28.5%

Operator B..................$ 30.30       6.10+28.5%

Classifications

Journeyman Specialist: Refers to a crew of only one person

working alone.

Operator A: Shall be proficient in operating all power

equipment including: Backhoe,

Excavator, Directional Bore and Boom/Digger truck.

Operator B: Shall be proficient in operating any 2 of the

above mentioned pieces of

equipment listed under Operator A.

----------------------------------------------------------------

ENGI0324-003 06/01/2017

ALCONA, ALPENA, ARENAC, BAY, CHEBOYGAN, CLARE, CLINTON,

CRAWFORD, GENESEE, GLADWIN, GRATIOT, HURON, INGHAM, IOSCO,

ISABELLA, JACKSON, LAPEER, LENAWEE, LIVINGSTON, MACOMB,

MIDLAND, MONROE, MONTMORENCY, OAKLAND, OGEMAW, OSCODA, OTSEGO,

PRESQUE ISLE, ROSCOMMON, SAGINAW, ST. CLAIR, SANILAC,

SHIAWASSEE, TUSCOLA, WASHTENAW AND WAYNE COUNTIES:

Rates          Fringes

OPERATOR:  Power Equipment

(Steel Erection)

GROUP  1....................$ 44.32            23.00

GROUP  2....................$ 45.32            23.00

GROUP  3....................$ 42.82            23.00

GROUP  4....................$ 43.82            23.00

GROUP  5....................$ 41.32            23.00

GROUP  6....................$ 42.32            23.00

GROUP  7....................$ 41.05            23.00

GROUP  8....................$ 42.05            23.00

GROUP  9....................$ 40.60            23.00

GROUP 10....................$ 41.60            23.00

GROUP 11....................$ 39.87            23.00

GROUP 12....................$ 40.87            23.00

GROUP 13....................$ 39.51            23.00

GROUP 14....................$ 40.51            23.00

GROUP 15....................$ 38.87            23.00

GROUP 16....................$ 37.17            23.00

GROUP 17....................$ 32.06            23.00

GROUP 18....................$ 30.65            23.00

FOOTNOTE:

Paid Holidays: New Year's Day, Memorial Day, Fourth of July,

Labor Day, Thanksgiving Day and Christmas Day.

POWER EQUIPMENT OPERATOR CLASSIFICATIONS

GROUP 1: Engineer when operating combination of boom and jib

400' or longer

GROUP 2: Engineer when operating combination of boom and jib

400' or longer on a crane that requires an oiler

GROUP 3: Engineer when operating combination of boom and jib

300' or longer

GROUP 4: Engineer when operating combination of boom and jib

300' or longer on a crane that requires an oiler

GROUP 5: Engineer when operating combination of boom and jib

220' or longer

GROUP 6: Engineer when operating combination of boom and jib

220' or longer on a crane that requires an oiler

GROUP 7: Engineer when operating combination of boom and jib

140' or longer

GROUP 8: Engineer when operating combination of boom and jib

140' or longer on a crane that requires an oiler

GROUP 9: Tower crane & derrick operator (where operator's

work station is 50 ft. or more above first sub-level)

GROUP 10: Tower crane & derrick operator (where operator's

work station is 50 ft. or more above first sub-level) on a

crane that requires an oiler

GROUP 11: Engineer when operating combination of boom and jib

120' or longer

GROUP 12: Engineer when operating combination of boom and jib

120' or longer on a crane that requires an oiler

GROUP 13: Crane operator; job mechanic  and 3 drum hoist and

excavator

GROUP 14: Crane operator on a crane that requires an oiler

GROUP 15: Hoisting operator; 2 drum hoist and rubber tired

backhoe

GROUP 16: Forklift and 1 drum hoist

GROUP 17: Compressor or welder operator

GROUP 18: Oiler

----------------------------------------------------------------

ENGI0324-004 06/01/2017

AREA 1: ALLEGAN, BARRY, BERRIEN, BRANCH, CALHOUN, CASS, EATON,

HILLSDALE, IONIA, KALAMAZOO, KENT, LAKE, MANISTEE, MASON,

MECOSTA, MONTCALM, MUSKEGON, NEWAYGO, OCEANA, OSCEOLA, OTTAWA,

ST. JOSEPH, VAN BUREN

AREA 2: ANTRIM, BENZIE, CHARLEVOIX, EMMET, GRAND TRAVERSE,

KALKASKA, LEELANAU, MISSAUKEE AND WEXFORD COUNTIES:

Rates          Fringes

OPERATOR:  Power Equipment

(Steel Erection)

AREA 1

GROUP 1....................$ 44.32            23.00

GROUP 2....................$ 41.05            23.00

GROUP 3....................$ 39.51            23.00

GROUP 4....................$ 37.17            23.00

GROUP 5....................$ 32.06            23.00

GROUP 6....................$ 30.65            23.00

AREA 2

GROUP 1....................$ 44.32            23.00

GROUP 2....................$ 41.05            23.00

GROUP 3....................$ 39.51            23.00

GROUP 4....................$ 37.17            23.00

GROUP 5....................$ 32.06            23.00

GROUP 6....................$ 30.65            23.00

FOOTNOTES:

Crane operator with main boom and jib 300' or longer: $1.50

additional to the group 1 rate.  Crane operator with main

boom and jib 400' or longer: $3.00 additional to the group

1 rate.

PAID HOLIDAYS: New Year's Day, Memorial Day, Fourth of July,

Labor Day, Thanksgiving Day and Christmas Day.

POWER EQUIPMENT OPERATOR CLASSIFICATIONS:

GROUP 1: Crane Operator with main boom & jib 400', 300', or

220' or longer.

GROUP 2: Crane Operator with main boom & jib 140' or longer,

Tower Crane; Gantry Crane; Whirley Derrick.

GROUP 3: Regular Equipment Operator, Crane, Dozer, Loader,

Hoist, Straddle Wagon, Mechanic, Grader and Hydro Excavator.

GROUP 4: Air Tugger (single drum), Material Hoist Pump 6" or

over, Elevators, Brokk Concrete Breaker.

GROUP 5: Air Compressor, Welder, Generators, Conveyors

GROUP 6: Oiler and fire tender

----------------------------------------------------------------

ENGI0324-005 09/01/2017

AREA 1: GENESEE, LAPEER, LIVINGSTON, MACOMB, MONROE, OAKLAND,

ST. CLAIR, WASHTENAW AND WAYNE COUNTIES

AREA 2: ALCONA, ALLEGAN, ALGER, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY,  BAY,  BENZIE, BERRIEN, BRANCH, CALHOUN, CASS,

CHARLEVOIX, CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD,

DELTA, DICKINSON, EATON, EMMET, GLADWIN, GOGEBIC, GRAND

TRAVERSE, GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM, IONIA,

IOSCO, IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT,

KWEENAW, LAKE, LEELANAU, LENAWEE, LUCE, MACKINAC, MANISTEE,

MARQUETTE, MASON, MECOSTA, MENOMINEE, MIDLAND,  MISSAUKEE,

MONTCALM, MONTMORENCY, MUSKEGON, NEWAYGO, OCEANA, OGEMAW,

ONTONAGON, OSCEOLA, OSCODA, OTSEGO, OTTAWA, PRESQUE ISLE,

ROSCOMMON, SAGINAW, SANILAC, SCHOOLCRAFT, SHIAWASSEE, ST.

JOSEPH, TUSCOLA, VAN BUREN AND WEXFORD COUNTIES

Rates          Fringes

OPERATOR:  Power Equipment

(Underground construction

(including sewer))

AREA 1:

GROUP 1....................$ 32.03            23.35

GROUP 2....................$ 27.30            23.35

GROUP 3....................$ 26.57            23.35

GROUP 4....................$ 26.00            23.35

AREA 2:

GROUP 1....................$ 30.32            23.35

GROUP 2....................$ 25.43            23.35

GROUP 3....................$ 24.93            23.35

GROUP 4....................$ 24.65            23.35

POWER EQUIPMENT OPERATOR CLASSIFICATIONS

GROUP 1: Backfiller tamper; Backhoe; Batch plant operator

(concrete); Clamshell; Concrete paver (2 drums or larger);

Conveyor loader (Euclid type); Crane (crawler, truck type

or pile driving); Dozer; Dragline; Elevating grader;

Endloader; Gradall (and similar type machine); Grader;

Mechanic; Power shovel; Roller (asphalt); Scraper

(self-propelled or tractor drawn); Side boom tractor (type

D-4 or equivalent and larger); Slip form paver; Slope

paver; Trencher (over 8 ft. digging capacity); Well

drilling rig; Concrete pump with boom operator; Hydro

Excavator

GROUP 2: Boom truck (power swing type boom); Crusher; Hoist;

Pump (1 or more - 6-in. discharge or larger - gas or

diesel- powered or powered by generator of 300 amperes or

more - inclusive of generator); Side boom tractor (smaller

than type D-4 or equivalent); Tractor (pneu-tired, other

than backhoe or front end loader); Trencher (8-ft. digging

capacity and smaller);Vac Truck

GROUP 3: Air compressors (600 cfm or larger); Air compressors

(2 or more-less than 600 cfm); Boom truck (non-swinging,

non- powered type boom); Concrete breaker (self-propelled

or truck mounted - includes compressor); Concrete paver (1

drum-l/2 yd. or larger); Elevator (other than passenger);

Maintenance person; Pump (2 or more-4-in. up to 6-in.

discharge-gas or diesel powered - excluding submersible

pumps); Pumpcrete machine (and similar equipment); Wagon

drill (multiple); Welding machine or generator (2 or

more-300 amp. or larger - gas or diesel powered)

GROUP 4: Boiler; Concrete saw (40 hp or over); Curing machine

(self-propelled); Farm tractor (with attachment); Finishing

machine (concrete); Fire person; Hydraulic pipe pushing

machine; Mulching equipment; Oiler; Pumps (2 or more up to

4-in. discharge, if used 3 hours or more a day, gas or

diesel powered - excluding submersible pumps); Roller

(other than asphalt); Stump remover; Trencher (service);

Vibrating compaction equipment, self-propelled (6 ft. wide

or over); End dump operator; Sweeper (Wayne type); Water

wagon and Extend-a boom forklift

----------------------------------------------------------------

ENGI0324-006 06/01/2017

AREA 1: GENESEE, MACOMB, MONROE, OAKLAND, WASHTENAW AND WAYNE

COUNTIES

AREA 2: ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY, BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GLADWIN, GOGEBIC, GRAND TRAVERSE,

GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM, IONIA, IOSCO,

IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT, KEWEENAW,

LAKE, LAPEER,  LEELANAU, LENAWEE, LIVINGSTON, LUCE, MACKINAC,

MANISTEE, MARQUETTE, MASON, MECOSTA, MENOMINEE, MIDLAND,

MISSAUKEE, MONTCALM, MONTMORENCY, MUSKEGON, NEWAYGO, OCEANA,

OGEMAW, ONTONAGON, OSCEOLA, OSCODA, OTSEGO, OTTAWA, PRESQUE

ISLE, ROSCOMMON, SAGINAW, ST. CLARE, ST. JOSEPH, SANILAC,

SCHOOLCRAFT, SHIAWASSEE, TUSCOLA, VAN BUREN AND WEXFORD COUNTIES

Rates          Fringes

Power equipment operators:

(AIRPORT, BRIDGE & HIGHWAY

CONSTRUCTION)

AREA 1

GROUP 1....................$ 32.16            23.35

GROUP 2....................$ 25.43            23.35

GROUP 3....................$ 26.73            23.35

GROUP 4....................$ 24.87            23.35

GROUP 5....................$ 24.70            23.35

AREA 2

GROUP 1....................$ 32.16            23.35

GROUP 2....................$ 25.28            23.35

GROUP 3....................$ 26.58            23.35

GROUP 4....................$ 24.72            23.35

GROUP 5....................$ 24.40            23.35

POWER EQUIPMENT OPERATOR CLASSIFICATIONS

GROUP 1: Asphalt plant operator; Crane operator (does not

include work on bridge construction projects when the crane

operator is erecting structural components); Dragline

operator; Shovel operator; Locomotive operator; Paver

operator (5 bags or more); Elevating grader operator; Pile

driving operator; Roller operator (asphalt); Blade grader

operator; Trenching machine operator (ladder or wheel

type); Auto-grader; Slip form paver; Self-propelled or

tractor-drawn scraper; Conveyor loader operator (Euclid

type); Endloader operator (1 yd. capacity and over);

Bulldozer; Hoisting engineer; Tractor operator; Finishing

machine operator (asphalt); Mechanic; Pump operator (6-in.

discharge or over, gas, diesel powered or generator of 300

amp. or larger); Shouldering or gravel distributing machine

operator (self- propelled); Backhoe (with over 3/8 yd.

bucket); Side boom tractor (type D-4 or equivalent or

larger); Tube finisher (slip form paving); Gradall (and

similar type machine); Asphalt paver (self- propelled);

Asphalt planer (self-propelled); Batch plant

(concrete-central mix); Slurry machine (asphalt); Concrete

pump (3 in. and over); Roto-mill; Swinging boom truck (over

12 ton capacity); Hydro demolisher (water blaster);

Farm-type tractor with attached pan

GROUP 2: Screening plant operator; Washing plant operator;

Crusher operator; Backhoe (with 3/8 yd. bucket or less);

Side boom tractor (smaller than D-4 type or equivalent);

Sweeper (Wayne type and similar equipment); Vacuum truck

operator; Batch plant (concrete dry batch)

GROUP 3: Grease Truck

GROUP 4: Air compressor operator (600 cu. ft. per min or

more); Air compressor operator (two or more, less than 600

cfm); Wagon drill operator; Concrete breaker; Tractor

operator (farm type with attachment)

GROUP 5: Boiler fire tender; Oiler; Fire tender; Trencher

(service); Flexplane operator; Cleftplane operator; Grader

operator (self-propelled fine-grade or form (concrete));

Finishing machine operator (concrete); Boom or winch hoist

truck operator; Endloader operator (under 1 yd. capacity);

Roller operator (other than asphalt); Curing equipment

operator (self-propelled); Concrete saw operator (40 h.p.

or over); Power bin operator; Plant drier operator

(asphalt); Vibratory compaction equipment operator (6 ft.

wide or over); Guard post driver operator (power driven);

All mulching equipment; Stump remover; Concrete pump (under

3-in.); Mesh installer (self- propelled); Tractor operator

(farm type); End dump; Skid steer

----------------------------------------------------------------

ENGI0324-007 05/01/2017

ALGER, BARAGA, CHIPPEWA, DELTA, DICKINSON, GOGEBIC, HOUGHTON,

IRON, KEWEENAW, LUCE, MACKINAC MARQUETTE, MENOMINEE, ONTONAGON

AND SCHOOLCRAFT COUNTIES:

Rates          Fringes

OPERATOR:  Power Equipment

(Steel Erection)

Compressor, welder and

forklift....................$ 25.71            23.05

Crane operator, main boom

& jib 120' or longer........$ 29.46            23.05

Crane operator, main boom

& jib 140' or longer........$ 29.71            23.05

Crane operator, main boom

& jib 220' or longer........$ 29.96            23.05

Mechanic with truck and

tools.......................$ 30.46            23.05

Oiler and fireman...........$ 24.41            23.05

Regular operator............$ 28.96            23.05

----------------------------------------------------------------

ENGI0324-008 10/01/2015

ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA, BARRY,

BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GENESEE, GLADWIN, GOGEBIC, GRAND

TRAVERSE, GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM, IONIA,

IOSCO, IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT,

KEWEENAW, LAKE, LAPEER,  LEELANAU, LENAWEE, LIVINGSTON, LUCE,

MACKINAC, MACOMB, MANISTEE, MARQUETTE, MASON, MECOSTA,

MENOMINEE, MIDLAND, MISSAUKEE, MONTCALM, MONTMORENCY, MONROE,

MUSKEGON, NEWAYGO, OAKLAND, OCEANA, OGEMAW, ONTONAGON, OSCEOLA,

OSCODA, OTSEGO, OTTAWA, PRESQUE ISLE, ROSCOMMON, SAGINAW, ST.

CLARE, ST. JOSEPH, SANILAC, SCHOOLCRAFT, SHIAWASSEE, TUSCOLA,

VAN BUREN, WASHTENAW, WAYNE AND WEXFORD COUNTIES

Rates          Fringes

OPERATOR:  Power Equipment

(Sewer Relining)

GROUP 1.....................$ 30.70            12.93

GROUP 2.....................$ 29.17            12.93

SEWER RELINING CLASSIFICATIONS

GROUP 1: Operation of audio-visual closed circuit TV system,

including remote in-ground cutter and other equipment used

in connection with the CCTV system

GROUP 2: Operation of hot water heaters and circulation

systems, water jetters and vacuum and mechanical debris

removal systems

----------------------------------------------------------------

ENGI0325-012 05/01/2017

AREA 1: MACOMB, MONROE, OAKLAND, ST. CLAIR, WASHTENAW AND WAYNE

COUNTIES

AREA 2: ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY, BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GENESEE, GLADWIN, GOGEBIC, GRAND

TRAVERSE, GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM, IONIA,

IOSCO, IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT,

KEWEENAW, LAKE, LAPEER,  LEELANAU, LENAWEE, LIVINGSTON LUCE,

MACKINAC, MANISTEE, MARQUETTE, MASON, MECOSTA, MENOMINEE,

MIDLAND, MISSAUKEE, MONTCALM, MONTMORENCY, MUSKEGON, NEWAYGO,

OCEANA, OGEMAW, ONTONAGON, OSCEOLA, OSCODA, OTSEGO, OTTAWA,

PRESQUE ISLE, ROSCOMMON, SAGINAW,  ST. JOSEPH, SANILAC,

SCHOOLCRAFT, SHIAWASSEE, TUSCOLA, VAN BUREN AND WEXFORD COUNTIES

Rates          Fringes

Power equipment operators -

gas distribution and duct

installation work:

AREA 1

GROUP 1....................$ 29.73            23.30

GROUP 2....................$ 29.60            23.30

GROUP 3....................$ 28.48            23.30

GROUP 4....................$ 27.90            23.30

AREA 2

GROUP 1....................$ 28.82            23.30

GROUP 2-A..................$ 28.72            23.30

GROUP 2-B..................$ 28.50            23.30

GROUP 3....................$ 27.72            23.30

GROUP 4....................$ 27.22            23.30

SCOPE OF WORK: The construction, installation, treating and

reconditioning of pipelines transporting gas vapors within

cities, towns, subdivisions, suburban areas, or within

private property boundaries, up to and including private

meter settings of private industrial, governmental or other

premises, more commonly referred to as "distribution work,"

starting from the first metering station, connection,

similar or related facility, of the main or cross country

pipeline and including duct installation.

AREA 1:

GROUP 1: Backhoe, crane, grader, mechanic, dozer (D-6

equivalent or larger), side boom (D-4 equivalent or

larger), trencher(except service), endloader (2 yd.

capacity or greater).

GROUP 2: Dozer (less than D-6 equivalent), endloader (under 2

yd. capacity), side boom (under D-4 capacity), backfiller,

pumps (1 or 2 of 6-inch discharge or greater), boom truck

(with powered boom), tractor (wheel type other than backhoe

or front endloader).

GROUP 3: Tamper (self-propelled), boom truck (with

non-powered boom), concrete saw (20 hp or larger), pumps (2

to 4 under 6-inch discharge), compressor (2 or more or when

one is used continuously into the second day) and

trencher(service).

GROUP 4: Oiler, hydraulic pipe pushing machine, grease person

and hydrostatic testing operator.

AREA 2:

GROUP 1: Mechanic, crane (over 1/2 yd. capacity), backhoe

(over 1/2 yd. capacity), grader (Caterpillar 12 equivalent

or larger)

GROUP 2-A: Trencher(except service), backhoe (1/2 yd.

capacity or less)

GROUP 2-B: Crane (1/2 yd. capacity or less), compressor (2 or

more), dozer (D-4 equivalent or larger), endloader (1 yd.

capacity or larger), pump (1 or 2 six-inch or larger), side

boom (D-4 equivalent or larger)

GROUP 3: Backfiller, boom truck (powered), concrete saw (20

hp or larger), dozer (less than D-4 equivalent), endloader

(under 1 yd. capacity), farm tractor (with attachments),

pump (2 - 4 under six-inch capacity), side boom

tractor(less than D-4 equivalent), tamper (self-propelled),

trencher service and grader maintenance

GROUP 4: Oiler, grease person and hydrostatic testing operator

----------------------------------------------------------------

* IRON0008-007 06/01/2017

ALGER, BARAGA, CHIPPEWA, DELTA, DICKINSON, GOGEBIC, HOUGHTON,

IRON, KEWEENAW, LUCE, MACKINAC MARQUETTE, MENOMINEE, ONTONAGON

AND SCHOOLCRAFT COUNTIES:

Rates          Fringes

Ironworker - pre-engineered

metal building erector...........$ 23.70             6.95

IRONWORKER

General contracts

$10,000,000 or greater......$ 30.17            26.40

General contracts less

than $10,000,000............$ 30.17            26.40

Paid Holidays: New Year's Day, Memorial Day, July 4th, Labor

Day, Thanksgiving Day & Christmas Day.

----------------------------------------------------------------

* IRON0025-002 06/01/2017

ALCONA, ALPENA, ARENAC, BAY, CHEBOYGAN, CLARE, CLINTON,

CRAWFORD, GENESEE, GLADWIN, GRATIOT, HURON, INGHAM, IOSCO,

ISABELLA, JACKSON, LAPEER, LIVINGSTON, MACOMB, MIDLAND,

MONTMORENCY, OAKLAND, OGEMAW, OSCODA, OTSEGO, PRESQUE ISLE,

ROSCOMMON, SAGINAW, SANILAC, SHIAWASSEE, ST. CLAIR, TUSCOLA,

WASHTENAW AND WAYNE COUNTIES:

Rates          Fringes

Ironworker - pre-engineered

metal building erector

Alcona, Alpena, Arenac,

Cheboygan, Clare, Clinton,

Crawford, Gladwin,

Gratiot, Huron, Ingham,

Iosco, Isabella, Jackson,

Lapeer, Livingston (west

of Burkhardt Road),

Montmorency, Ogemaw,

Oscoda, Otsego, Presque

Isle, Roscommon, Sanilac,

Shiawassee, Tuscola &

Washtenaw (west of U.S. 23).$ 22.17            20.13

Bay, Genesee, Lapeer,

Livingston (east of

Burkhardt Road), Macomb,

Midland, Oakland, Saginaw,

St. Clair, The University

of Michigan, Washtenaw

(east of U.S. 23) & Wayne...$ 23.39            21.13

IRONWORKER

Ornamental and Structural...$ 29.99            33.43

Reinforcing.................$ 26.57            26.90

----------------------------------------------------------------

IRON0055-005 07/01/2017

LENAWEE AND MONROE COUNTIES:

Rates          Fringes

IRONWORKER

Pre-engineered metal

buildings...................$ 23.59            19.35

All other work..............$ 29.77            21.30

----------------------------------------------------------------

IRON0292-003 06/01/2017

BERRIEN AND CASS COUNTIES:

Rates          Fringes

IRONWORKER (Including

pre-engineered metal building

erector).........................$ 29.30            20.96

----------------------------------------------------------------

IRON0340-001 06/19/2017

ALLEGAN, ANTRIM, BARRY, BENZIE, BRANCH, CALHOUN, CHARLEVOIX,

EATON, EMMET, GRAND TRAVERSE, HILLSDALE, IONIA, KALAMAZOO,

KALKASKA, KENT, LAKE, LEELANAU, MANISTEE, MASON, MECOSTA,

MISSAUKEE, MONTCALM, MUSKEGON, NEWAYGO, OCEANA, OSCEOLA,

OTTAWA, ST. JOSEPH, VAN BUREN AND WEXFORD COUNTIES:

Rates          Fringes

IRONWORKER (Including

pre-engineered metal building

erector).........................$ 24.43            24.67

----------------------------------------------------------------

LABO0005-006 10/01/2017

Rates          Fringes

Laborers - hazardous waste

abatement: (ALCONA, ALPENA,

ANTRIM, BENZIE, CHARLEVOIX,

CHEBOYGAN, CRAWFORD, EMMET,

GRAND TRAVERSE, IOSCO,

KALKASKA, LEELANAU,

MISSAUKEE, MONTMORENCY,

OSCODA, OTSEGO, PRESQUE ISLE

AND WEXFORD COUNTIES - Zone

10)

Levels A, B or C............$ 17.45            12.75

class b....................$ 18.00            12.85

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 16.45            12.75

class a....................$ 17.00            12.85

Zone 10

Laborers - hazardous waste

abatement: (ALGER, BARAGA,

CHIPPEWA, DELTA, DICKINSON,

GOGEBIC, HOUGHTON, IRON,

KEWEENAW, LUCE, MACKINAC,

MARQUETTE, MENOMINEE,

ONTONAGON AND SCHOOLCRAFT

COUNTIES - Zone 11)

Levels A, B or C............$ 21.63            12.88

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 20.63            12.88

Laborers - hazardous waste

abatement: (ALLEGAN, BARRY,

BERRIEN, BRANCH, CALHOUN,

CASS, IONIA COUNTY (except

the city of Portland);

KALAMAZOO, KENT, LAKE,

MANISTEE, MASON, MECOSTA,

MONTCALM, MUSKEGON, NEWAYGO,

OCEANA, OSCEOLA, OTTAWA, ST.

JOSEPH AND VAN BUREN COUNTIES

- Zone 9)

Levels A, B or C............$ 20.95            12.85

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 19.95            12.85

Laborers - hazardous waste

abatement: (ARENAC, BAY,

CLARE, GLADWIN, GRATIOT,

HURON, ISABELLA, MIDLAND,

OGEMAW, ROSCOMMON, SAGINAW

AND TUSCOLA COUNTIES - Zone 8)

Levels A, B or C............$ 20.65            12.85

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 19.65            12.85

Laborers - hazardous waste

abatement: (CLINTON, EATON

AND INGHAM COUNTIES; IONIA

COUNTY (City of Portland);

LIVINGSTON COUNTY (west of

Oak Grove Rd., including the

City of Howell) - Zone 6)

Levels A, B or C............$ 24.65            12.85

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 23.65            12.85

Laborers - hazardous waste

abatement: (GENESEE, LAPEER

AND SHIAWASSEE COUNTIES -

Zone 7)

Levels A, B or C............$ 23.61            13.41

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 22.61            13.41

Laborers - hazardous waste

abatement: (HILLSDALE,

JACKSON AND LENAWEE COUNTIES

- Zone 4)

Levels A, B or C............$ 24.19            12.85

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 23.19            12.85

Laborers - hazardous waste

abatement: (LIVINGSTON COUNTY

(east of Oak Grove Rd. and

south of M-59, excluding the

city of Howell); AND

WASHTENAW COUNTY - Zone 3)

Levels A, B or C............$ 25.50            18.40

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 24.50            18.40

Laborers - hazardous waste

abatement: (MACOMB AND WAYNE

COUNTIES - Zone 1)

Levels A, B or C............$ 25.35            20.25

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 24.35            20.25

Laborers - hazardous waste

abatement: (MONROE COUNTY -

Zone 4)

Levels A, B or C............$ 26.44            18.85

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 25.44            18.85

Laborers - hazardous waste

abatement: (OAKLAND COUNTY

and the Northeast portion of

LIVINGSTON COUNTY bordered by

Oak Grove Road on the West

and M-59 on the South - Zone

2)

Level A, B, C...............$ 25.35            20.25

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 24.35            20.25

Laborers - hazardous waste

abatement: (SANILAC AND ST.

CLAIR COUNTIES - Zone 5)

Levels A, B or C............$ 25.19            15.86

Work performed in

conjunction with site

preparation not requiring

the use of personal

protective equipment;

Also, Level D...............$ 24.19            15.86

----------------------------------------------------------------

LABO0259-001 09/01/2017

AREA 1: MACOMB, OAKLAND AND WAYNE COUNTIES

AREA 2: ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY, BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GENESEE, GLADWIN, GOGEBIC, GRAND

TRAVERSE, GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM, IONIA,

IOSCO, IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT,

KEWEENAW, LAKE, LAPEER,  LEELANAU, LENAWEE, LIVINGSTON, LUCE,

MACKINAC, MANISTEE, MARQUETTE, MASON, MECOSTA, MENOMINEE,

MIDLAND, MISSAUKEE, MONROE, MONTCALM, MONTMORENCY, MUSKEGON,

NEWAYGO, OCEANA, OGEMAW, ONTONAGON, OSCEOLA, OSCODA, OTSEGO,

OTTAWA, PRESQUE ISLE, ROSCOMMON, SAGINAW, ST. CLARE, ST.

JOSEPH, SANILAC, SCHOOLCRAFT, SHIAWASSEE, TUSCOLA, VAN BUREN,

WASHTENAW AND WEXFORD COUNTIES

Rates          Fringes

Laborers - tunnel, shaft and

caisson:

AREA 1

GROUP 1....................$ 22.22            16.75

GROUP 2....................$ 22.33            16.75

GROUP 3....................$ 22.39            16.75

GROUP 4....................$ 22.57            16.75

GROUP 5....................$ 22.82            16.75

GROUP 6....................$ 23.15            16.75

GROUP 7....................$ 16.43            16.75

AREA 2

GROUP 1....................$ 23.75            12.85

GROUP 2....................$ 23.84            12.85

GROUP 3....................$ 23.94            12.85

GROUP 4....................$ 24.10            12.85

GROUP 5....................$ 24.38            12.85

GROUP 6....................$ 24.67            12.85

GROUP 7....................$ 16.94            12.85

SCOPE OF WORK: Tunnel, shaft and caisson work of every type

and description and all operations incidental thereto,

including, but not limited to, shafts and tunnels for

sewers, water, subways, transportation, diversion,

sewerage, caverns, shelters, aquafers, reservoirs, missile

silos and steel sheeting for underground construction.

TUNNEL LABORER CLASSIFICATIONS

GROUP 1: Tunnel, shaft and caisson laborer, dump, shanty, hog

house tender, testing (on gas) and watchman

GROUP 2: Manhole, headwall, catch basin builder, bricklayer

tender, mortar machine and material mixer

GROUP 3: Air tool operator (jackhammer, bush hammer and

grinder), first bottom, second bottom, cage tender, car

pusher, carrier, concrete, concrete form, concrete repair,

cement invert laborer, cement finisher, concrete shoveler,

conveyor, floor, gasoline and electric tool operator,

gunite, grout operator, welder, heading dinky person,

inside lock tender, pea gravel operator, pump, outside lock

tender, scaffold, top signal person, switch person, track,

tugger, utility person, vibrator, winch operator, pipe

jacking, wagon drill and air track operator and concrete

saw operator (under 40 h.p.)

GROUP 4: Tunnel, shaft and caisson mucker, bracer, liner

plate, long haul dinky driver and well point

GROUP 5: Tunnel, shaft and caisson miner, drill runner, key

board operator, power knife operator, reinforced steel or

mesh (e.g. wire mesh, steel mats, dowel bars, etc.)

GROUP 6: Dynamite and powder

GROUP 7: Restoration laborer, seeding, sodding, planting,

cutting, mulching and top soil grading; and the restoration

of property such as replacing mailboxes, wood chips,

planter boxes, flagstones, etc.

----------------------------------------------------------------

LABO0334-001 09/01/2017

Rates          Fringes

Laborers - open cut:

ZONE 1 - MACOMB, OAKLAND

AND WAYNE COUNTIES:

GROUP 1....................$ 22.07            16.70

GROUP 2....................$ 22.18            16.75

GROUP 3....................$ 22.23            16.75

GROUP 4....................$ 22.31            16.75

GROUP 5....................$ 22.37            16.75

GROUP 6....................$ 19.82            16.75

GROUP 7....................$ 16.44            16.75

ZONE 2 - LIVINGSTON COUNTY

(east of M-151 (Oak Grove

Rd.)); MONROE AND

WASHTENAW   COUNTIES:

GROUP 1....................$ 23.40            12.85

GROUP 2....................$ 23.51            12.85

GROUP 3....................$ 23.63            12.85

GROUP 4....................$ 23.70            12.85

GROUP 5....................$ 23.85            12.85

GROUP 6....................$ 21.15            12.85

GROUP 7....................$ 17.79            12.85

ZONE 3 - CLINTON, EATON,

GENESEE, HILLSDALE AND

INGHAM COUNTIES; IONIA

COUNTY (City of Portland);

JACKSON, LAPEER AND

LENAWEE COUNTIES;

LIVINGSTON COUNTY (west of

M-151 Oak Grove Rd.);

SANILAC, ST. CLAIR AND

SHIAWASSEE COUNTIES:

GROUP 1....................$ 21.59            12.85

GROUP 2....................$ 21.73            12.85

GROUP 3....................$ 21.85            12.85

GROUP 4....................$ 21.90            12.85

GROUP 5....................$ 22.04            12.85

GROUP 6....................$ 19.34            12.85

GROUP 7....................$ 16.49            12.85

ZONE 4 - ALCONA, ALLEGAN,

ALPENA, ANTRIM, ARENAC,

BARRY, BAY, BENZIE,

BERRIEN,   BRANCH,

CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CLARE,

CRAWFORD, EMMET,

GLADWIN, GRAND TRAVERSE,

GRATIOT AND HURON

COUNTIES; IONIA COUNTY

(EXCEPT THE CITY OF

PORTLAND); IOSCO,

ISABELLA, KALAMAZOO,

KALKASKA, KENT,

LAKE,LEELANAU, MANISTEE,

MASON, MECOSTA, MIDLAND,

MISSAUKEE, MONTCALM,

MONTMORENCY, MUSKEGON,

NEWAYGO, OCEANA, OGEMAW,

OSCEOLA, OSCODA, OTSEGO,

OTTAWA, PRESQUE ISLE,

ROSCOMMON, SAGINAW, ST.

JOSEPH, TUSCOLA, VAN BUREN

AND WEXFORD COUNTIES:

GROUP 1....................$ 20.60            12.85

GROUP 2....................$ 20.73            12.85

GROUP 3....................$ 20.84            12.85

GROUP 4....................$ 20.91            12.85

GROUP 5....................$ 21.03            12.85

GROUP 6....................$ 18.25            12.85

GROUP 7....................$ 16.59            12.85

ZONE 5 - ALGER, BARAGA,

CHIPPEWA, DELTA,

DICKINSON, GOGEBIC,

HOUGHTON, IRON,

KEWEENAW, LUCE, MACKINAC,

MARQUETTE, MENOMINEE,

ONTONAGON AND SCHOOLCRAFT

COUNTIES:

GROUP 1....................$ 20.81            12.85

GROUP 2....................$ 20.95            12.85

GROUP 3....................$ 21.08            12.85

GROUP 4....................$ 21.13            12.85

GROUP 5....................$ 21.18            12.85

GROUP 6....................$ 18.56            12.85

GROUP 7....................$ 16.67            12.85

SCOPE OF WORK:

Open cut construction work shall be construed to mean work

which requires the excavation of earth including

industrial, commercial and residential building site

excavation and preparation, land balancing, demolition and

removal of concrete and underground appurtenances, grading,

paving, sewers, utilities and improvements; retention,

oxidation, flocculation and irrigation facilities, and also

including but not limited to underground piping, conduits,

steel sheeting for underground construction, and all work

incidental thereto, and general excavation.  For all areas

except the Upper Peninsula, open cut construction work

shall also be construed to mean waterfront work, piers,

docks, seawalls, breakwalls, marinas and all incidental

work.   Open cut construction work shall not include any

structural modifications, alterations, additions and

repairs to buildings, or highway work, including roads,

streets, bridge construction and parking lots or steel

erection work and excavation for the building itself and

back filling inside of and within 5 ft. of the building and

foundations, footings and piers for the building.  Open cut

construction work shall not include any work covered under

Tunnel, Shaft and Caisson work.

OPEN CUT LABORER CLASSIFICATIONS

GROUP 1: Construction laborer

GROUP 2: Mortar and material mixer, concrete form person,

signal person, well point person, manhole, headwall and

catch basin builder, headwall, seawall, breakwall and dock

builder

GROUP 3: Air, gasoline and electric tool operator, vibrator

operator, driller, pump person, tar kettle operator,

bracer, rodder, reinforced steel or mesh person (e.g., wire

mesh, steel mats, dowel bars, etc.), welder, pipe jacking

and boring person, wagon drill and air track operator and

concrete saw operator (under 40 h.p.), windlass and tugger

person and directional boring person

GROUP 4: Trench or excavating grade person

GROUP 5: Pipe layer (including crock, metal pipe, multi-plate

or other conduits)

GROUP 6: Grouting man, audio-visual television operations and

all other operations in connection with closed circuit

television inspection, pipe cleaning and pipe relining work

and the installation and repair of water service pipe and

appurtenances

GROUP 7: Restoration laborer, seeding, sodding, planting,

cutting, mulching and top soil grading; and the restoration

of property such as replacing mailboxes, wood chips,

planter boxes, flagstones, etc.

----------------------------------------------------------------

LABO0465-001 06/01/2017

LABORER: Highway, Bridge and Airport Construction

AREA 1: GENESEE, MACOMB, MONROE, OAKLAND, WASHTENAW AND WAYNE

COUNTIES

AREA 2: ALLEGAN, BARRY, BAY, BERRIEN, BRANCH, CALHOUN, CASS,

CLINTON, EATON, GRATIOT, HILLSDALE, HURON, INGHAM, JACKSON,

KALAMAZOO, LAPEER, LENAWEE, LIVINGSTON, MIDLAND, MUSKEGON,

SAGINAW, SANILAC, SHIAWASSEE, ST. CLAIR, ST. JOSEPH, TUSCOLA

AND VAN BUREN COUNTIES

AREA 3:  ALCONA, ALPENA, ANTRIM, ARENAC, BENZIE, CHARLEVOIX,

CHEBOYGAN, CLARE, CRAWFORD, EMMET, GLADWIN, GRAND TRAVERSE,

IONIA, IOSCO, ISABELLA, KALKASKA, KENT, LAKE, LEELANAU,

MANISTEE, MASON, MECOSTA, MISSAUKEE, MONTCALM, MONTMORENCY,

NEWAYGO, OCEANA, OGEMAW, OSCEOLA, OSCODA, OTSEGO, OTTAWA,

PRESQUE ISLE, ROSCOMMON AND WEXFORD COUNTIES

AREA 4: ALGER, BARAGA, CHIPPEWA, DELTA, DICKINSON, GOGEBIC,

HOUGHTON, IRON, KEWEENAW, LUCE, MACKINAC, MARQUETTE, MENOMINEE,

ONTONAGON AND SCHOOLCRAFT COUNTIES

Rates          Fringes

LABORER (AREA 1)

GROUP 1.....................$ 25.74            12.85

GROUP 2.....................$ 25.87            12.85

GROUP 3.....................$ 26.05            12.85

GROUP 4.....................$ 26.13            12.85

GROUP 5.....................$ 26.34            12.85

GROUP 6.....................$ 26.64            12.85

LABORER (AREA 2)

GROUP 1.....................$ 23.67            12.85

GROUP 2.....................$ 23.87            12.85

GROUP 3.....................$ 24.11            12.85

GROUP 4.....................$ 24.46            12.85

GROUP 5.....................$ 24.33            12.85

GROUP 6.....................$ 24.67            12.85

LABORER (AREA 3)

GROUP 1.....................$ 22.92            12.85

GROUP 2.....................$ 23.13            12.85

GROUP 3.....................$ 23.42            12.85

GROUP 4.....................$ 23.86            12.85

GROUP 5.....................$ 23.48            12.85

GROUP 6.....................$ 23.91            12.85

LABORER (AREA 4)

GROUP 1.....................$ 22.94            12.85

GROUP 2.....................$ 23.15            12.85

GROUP 3.....................$ 23.44            12.85

GROUP 4.....................$ 23.88            12.85

GROUP 5.....................$ 23.50            12.85

GROUP 6.....................$ 23.93            12.85

LABORER CLASSIFICATIONS

GROUP 1: Asphalt shoveler or loader; asphalt plant misc.;

burlap person; yard person; dumper (wagon, truck, etc.);

joint filling laborer; miscellaneous laborer; unskilled

laborer; sprinkler laborer; form setting laborer; form

stripper; pavement reinforcing; handling and placing (e.g.,

wire mesh, steel mats, dowel bars); mason's tender or

bricklayer's tender on manholes; manhole builder;

headwalls, etc.; waterproofing,(other than buildings) seal

coating and slurry mix, shoring, underpinning; pressure

grouting; bridge pin and hanger removal; material recycling

laborer; horizontal paver laborer (brick, concrete, clay,

stone and asphalt); ground stabilization and modification

laborer; grouting; waterblasting; top person; railroad

track and trestle laborer; carpenters' tender; guard rail

builders' tender; earth retention barrier and wall and

M.S.E. wall installer's tender; highway and median

installer's tender(including sound, retaining, and crash

barriers); fence erector's tender; asphalt raker tender;

sign installer; remote control operated equipment.

GROUP 2: Mixer operator (less than 5 sacks); air or electric

tool operator (jackhammer, etc.); spreader; boxperson

(asphalt, stone, gravel); concrete paddler; power chain saw

operator; paving batch truck dumper; tunnel mucker (highway

work only); concrete saw (under 40 h.p.) and dry pack

machine; roto-mill grounds person.

GROUP 3: Tunnel miner (highway work only); finishers tenders;

guard rail builders; highway and median barrier installer;

earth retention barrier and wall and M.S.E. wall

installer's (including sound, retaining and crash

barriers); fence erector; bottom person; powder person;

wagon drill and air track operator; diamond and core

drills; grade checker; certified welders; curb and side

rail setter's tender.

GROUP 4: Asphalt raker

GROUP 5: Pipe layers, oxy-gun

GROUP 6: Line-form setter for curb or pavement; asphalt

screed checker/screw man on asphalt paving machines.

----------------------------------------------------------------

LABO1076-005 04/01/2017

MICHIGAN STATEWIDE

Rates          Fringes

LABORER (DISTRIBUTION WORK)

Zone 1......................$ 19.99            12.85

Zone 2......................$ 18.35            12.85

Zone 3......................$ 16.56            12.85

Zone 4......................$ 15.92            12.85

Zone 5......................$ 15.92            12.85

DISTRIBUTION WORK - The construction, installation, treating

and reconditioning of distribution pipelines transporting

coal, oil, gas or other similar materials, vapors or

liquids, including pipelines within private property

boundaries, up to and including the meter settings on

residential, commercial, industrial, institutional, private

and public structures. All work covering pumping stations

and tank farms not covered by the Building Trades

Agreement. Other distribution lines with the exception of

sewer, water and cable television are included.

Underground Duct Layer Pay: $.40 per hour above the base pay

rate.

Zone 1 - Macomb, Oakland and Wayne

Zone 2 - Monroe and Washtenaw

Zone 3 - Bay, Genesee, Lapeer, Midland, Saginaw, Sanilac,

Shiawassee and St. Clair

Zone 4 - Alger, Baraga, Chippewa, Delta, Dickinson, Gogebic,

Houghton, Iron, Keweenaw, Luce, Mackinac, Marquette,

Menominee, Ontonagon and Schoolcraft

Zone 5 - Remaining Counties in Michigan

----------------------------------------------------------------

PAIN0022-002 07/01/2008

HILLSDALE, JACKSON AND LENAWEE COUNTIES; LIVINGSTON COUNTY

(east of the eastern city limits of Howell, not including the

city of Howell, north to the Genesee County line and south to

the Washtenaw County line); MACOMB, MONROE, OAKLAND, WASHTENAW

AND WAYNE COUNTIES:

Rates          Fringes

PAINTER..........................$ 25.06            14.75

FOOTNOTES: For all spray work and journeyman rigging for

spray work, also blowing off, $0.80 per hour additional

(applies only to workers doing rigging for spray work on

off the floor work. Does not include setting up or moving

rigging on floor surfaces, nor does it apply to workers

engaged in covering up or tending spray equipment. For all

sandblasting and spray work performed on highway bridges,

overpasses, tanks or steel, $0.80 per hour additional. For

all brushing, cleaning and other preparatory work (other

than spraying or steeplejack work) at scaffold heights of

fifty (50) feet from the ground or higher, $0.50 per hour

additional. For all preparatorial work and painting

performed on open steel under forty (40) feet when no

scaffolding is involved, $0.50 per hour additional. For all

swing stage work-window jacks and window belts-exterior and

interior, $0.50 per hour additional. For all spray work and

sandblaster work to a scaffold height of forty (40) feet

above the floor level, $0.80 per hour additional. For all

preparatorial work and painting on all highway bridges or

overpasses up to forty (40) feet in height, $0.50 per hour

additional. For all steeplejack work performed where the

elevation is forty (40) feet or more, $1.25 per hour

additional.

----------------------------------------------------------------

PAIN0312-001 06/12/2014

EXCLUDES: ALLEGAN COUNTY (Townships of Dorr, Fillmore, Heath,

Hopkins, Laketown, Leighton, Manlius, Monterey, Overisel,

Salem, Saugatuck and Wayland);  INCLUDES: Barry, Berrien,

Branch, Calhoun, Cass, Hillsdale, Kalamazoo, St. Joseph, Van

Buren

Rates          Fringes

PAINTER

Brush and roller............$ 21.75            11.94

Spray, Sandblast, Sign

Painting....................$ 22.75            11.94

----------------------------------------------------------------

PAIN0845-003 05/21/2014

CLINTON COUNTY; EATON COUNTY (does not include the townships of

Bellevue and Olivet); INGHAM COUNTY; IONIA COUNTY (east of Hwy.

M 66); LIVINGSTON COUNTY (west of the eastern city limits of

Howell, including the city of Howell, north to the Genesee

County line and south to the Washtenaw County line); AND

SHIAWASSEE COUNTY (Townships of Bennington, Laingsbury and

Perry):

Rates          Fringes

PAINTER..........................$ 21.89            11.85

----------------------------------------------------------------

PAIN0845-015 05/21/2014

MUSKEGON COUNTY; NEWAYGO COUNTY (except the Townships of

Barton, Big Prairie, Brooks, Croton, Ensley, Everett, Goodwell,

Grant, Home, Monroe, Norwich and Wilcox); OCEANA COUNTY; OTTAWA

COUNTY (except the townships of Allendale, Blendone, Chester,

Georgetown, Holland, Jamestown, Olive, Park, Polkton, Port

Sheldon, Tallmadge, Wright and Zeeland):

Rates          Fringes

PAINTER..........................$ 21.89            11.85

----------------------------------------------------------------

PAIN0845-018 05/21/2014

ALLEGAN COUNTY (Townships of Dorr, Fillmore, Heath, Hopkins,

Laketown, Leighton, Manlius, Monterey, Overisel, Salem,

Saugatuck and Wayland); IONIA COUNTY (west of Hwy. M-66); KENT,

MECOSTA AND MONTCALM COUNTIES; NEWAYGO COUNTY (Townships of

Barton, Big Prairie, Brooks, Croton, Ensley, Everett, Goodwell,

Grant, Home, Monroe, Norwich and Wilcox); OSCEOLA COUNTY (south

of Hwy. #10); OTTAWA COUNTY (Townships of Allendale, Blendone,

Chester, Georgetown, Holland, Jamestown, Olive, Park, Polkton,

Port Sheldon, Tallmadge, Wright and Zeeland):

Rates          Fringes

PAINTER..........................$ 21.89            11.85

FOOTNOTES: Lead abatement work: $1.00 per hour additional.

----------------------------------------------------------------

PAIN1011-003 06/05/2014

ALGER, BARAGA, CHIPPEWA, DELTA, DICKINSON, GOGEBIC, HOUGHTON,

IRON, KEWEENAW, LUCE, MACKINAC, MARQUETTE, MENOMINEE, ONTONAGON

AND SCHOOLCRAFT COUNTIES:

Rates          Fringes

PAINTER..........................$ 24.15            10.52

FOOTNOTES: High pay (bridges, overpasses, watertower): 30 to

80 ft.: $.65 per hour additional. 80 ft. and over: $1.30

per hour additional.

----------------------------------------------------------------

PAIN1474-002 06/01/2010

HURON COUNTY; LAPEER COUNTY (east of Hwy. M-53); ST. CLAIR,

SANILAC AND TUSCOLA COUNTIES:

Rates          Fringes

PAINTER..........................$ 23.79            12.02

FOOTNOTES: Lead abatement work: $1.00 per hour additional.

Work with any hazardous material: $1.00 per hour

additional. Sandblasting, steam cleaning and acid cleaning:

$1.00 per hour additional. Ladder work at or above 40 ft.,

scaffold work at or above 40 ft., swing stage, boatswain

chair, window jacks and all work performed over a falling

height of 40 ft.: $1.00 per hour additional. Spray gun

work, pick pullers and those handling needles, blowing off

by air pressure, and any person rigging (setting up and

moving off the ground): $1.00 per hour additional.

Steeplejack, tanks, gas holders, stacks, flag poles, radio

towers and beacons, power line towers, bridges, etc.: $1.00

per hour additional, paid from the ground up.

----------------------------------------------------------------

PAIN1803-003 06/01/2017

ALCONA, ALPENA, ANTRIM, ARENAC, BAY, BENZIE, CHARLEVOIX,

CHEBOYGAN, CLARE, CRAWFORD, EMMET, GLADWIN, GRAND TRAVERSE,

GRATIOT, IOSCO, ISABELLA, KALKASKA, LAKE, LEELANAU, MANISTEE,

MASON, MIDLAND, MISSAUKEE, MONTMORENCY AND OGEMAW COUNTIES;

OSCEOLA COUNTY (north of Hwy. #10); OSCODA, OTSEGO, PRESQUE

ISLE, ROSCOMMON, SAGINAW AND WEXFORD COUNTIES:

Rates          Fringes

PAINTER

Work performed on water,

bridges over water or

moving traffic, radio and

powerline towers, elevated

tanks, steeples, smoke

stacks over 40 ft. of

falling heights, recovery

of lead-based paints and

any work associated with

industrial plants, except

maintenance of industrial

plants......................$ 25.10            13.85

All other work, including

maintenance of industrial

plant.......................$ 23.68            13.85

FOOTNOTES: Spray painting, sandblasting, blowdown associated

with spraying and blasting, water blasting and work

involving a swing stage, boatswain chair or spider: $1.00

per hour additional. All work performed inside tanks,

vessels, tank trailers, railroad cars, sewers, smoke

stacks, boilers or other spaces having limited egress not

including buildings, opentop tanks, pits, etc.: $1.25 per

hour additional.

----------------------------------------------------------------

PLAS0514-001 06/01/2017

ZONE 1: GENESEE, LIVINGSTON, MACOMB, MONROE, OAKLAND, SAGINAW,

WASHTENAW AND WAYNE COUNTIES

ZONE 2: ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY, BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GLADWIN, GOGEBIC, GRAND TRAVERSE,

GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM,  IONIA, IOSCO,

IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT, KEWEENAW,

LAKE, LAPEER, LEELANAU, LENAWEE, LUCE, MACKINAC, MANISTEE,

MARQUETTE, MASON, MECOSTA, MENOMINEE, MIDLAND, MISSAUKEE,

MONTCALM, MONTMORENCY, MUSKEGON, NEWAYGO, OCEANA, OGEMAW,

ONTONAGON, OSCEOLA, OSCODA, OTSEGO, OTTAWA, PRESQUE ISLE,

ROSCOMMON, SANILAC, SCHOOLCRAFT, SHIAWASSEE, ST. CLAIR, ST.

JOSEPH, TUSCOLA, VAN BUREN  AND WEXFORD COUNTIES

Rates          Fringes

CEMENT MASON/CONCRETE FINISHER

ZONE 1......................$ 30.94            13.59

ZONE 2......................$ 29.44            13.59

----------------------------------------------------------------

PLUM0190-003 05/01/2015

ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA, BARRY,

BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GENESEE, GLADWIN, GOGEBIC, GRAND

TRAVERSE, GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM, IONIA,

IOSCO, IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT,

KEWEENAW, LAKE, LAPEER,  LEELANAU, LENAWEE, LIVINGSTON, LUCE,

MACKINAC, MACOMB, MANISTEE, MARQUETTE, MASON, MECOSTA,

MENOMINEE, MIDLAND, MISSAUKEE, MONTCALM, MONTMORENCY, MONROE,

MUSKEGON, NEWAYGO, OAKLAND, OCEANA, OGEMAW, ONTONAGON, OSCEOLA,

OSCODA, OTSEGO, OTTAWA, PRESQUE ISLE, ROSCOMMON, SAGINAW, ST.

CLARE, ST. JOSEPH, SANILAC, SCHOOLCRAFT, SHIAWASSEE, TUSCOLA,

VAN BUREN, WASHTENAW, WAYNE AND WEXFORD COUNTIES

Rates          Fringes

Plumber/Pipefitter - gas

distribution pipeline:

Welding in conjunction

with gas distribution

pipeline work...............$ 33.03            20.19

All other work:.............$ 24.19            12.28

----------------------------------------------------------------

TEAM0007-004 06/01/2017

AREA 1: ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY, BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GLADWIN, GOGEBIC, GRAND TRAVERSE,

GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM,  IONIA, IOSCO,

IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT, KEWEENAW,

LAKE, LAPEER, LEELANAU, LENAWEE, LUCE, MACKINAC, MANISTEE,

MARQUETTE, MASON, MECOSTA, MENOMINEE, MIDLAND, MISSAUKEE,

MONTCALM, MONTMORENCY, MUSKEGON, NEWAYGO, OCEANA, OGEMAW,

ONTONAGON, OSCEOLA, OSCODA, OTSEGO, OTTAWA, PRESQUE ISLE,

ROSCOMMON, SAGINAW, SANILAC, SCHOOLCRAFT, SHIAWASSEE, ST.

CLAIR, ST. JOSEPH, TUSCOLA, VAN BUREN  AND WEXFORD COUNTIES

AREA 2: GENESEE, LIVINGSTON, MACOMB, MONROE, OAKLAND, WASHTENAW

AND WAYNE COUNTIES

Rates          Fringes

TRUCK DRIVER

AREA 1

Euclids, double bottoms

and lowboys................$ 25.05        .50 + a+b

Trucks under 8 cu. yds.....$ 24.80        .50 + a+b

Trucks, 8 cu. yds. and

over.......................$ 24.90        .50 + a+b

AREA 2

Euclids, double bottomms

and lowboys................$ 24.895       .50 + a+b

Euclids, double bottoms

and lowboys................$ 25.15        .50 + a+b

Trucks under 8 cu. yds.....$ 24.90        .50 + a+b

Trucks, 8 cu. yds. and

over.......................$ 25.00        .50 + a+b

Footnote:

a. $455.00 per week

b. $64.40 daily

----------------------------------------------------------------

TEAM0247-004 04/01/2013

AREA 1: ALCONA, ALGER, ALLEGAN, ALPENA, ANTRIM, ARENAC, BARAGA,

BARRY, BAY, BENZIE, BERRIEN, BRANCH, CALHOUN, CASS, CHARLEVOIX,

CHEBOYGAN, CHIPPEWA, CLARE, CLINTON, CRAWFORD, DELTA,

DICKINSON, EATON, EMMET, GLADWIN, GOGEBIC, GRAND TRAVERSE,

GRATIOT, HILLSDALE, HOUGHTON, HURON, INGHAM,  IONIA, IOSCO,

IRON, ISABELLA, JACKSON, KALAMAZOO, KALKASKA, KENT, KEWEENAW,

LAKE, LAPEER, LEELANAU, LENAWEE, LUCE, MACKINAC, MANISTEE,

MARQUETTE, MASON, MECOSTA, MENOMINEE, MIDLAND, MISSAUKEE,

MONTCALM, MONTMORENCY, MUSKEGON, NEWAYGO, OCEANA, OGEMAW,

ONTONAGON, OSCEOLA, OSCODA, OTSEGO, OTTAWA, PRESQUE ISLE,

ROSCOMMON, SANILAC, SCHOOLCRAFT, SHIAWASSEE, SAGINAW, ST.

CLAIR, ST. JOSEPH, TUSCOLA, VAN BUREN  AND WEXFORD COUNTIES

AREA 2: GENESEE, LIVINGSTON,  MACOMB, MONROE, OAKLAND,

WASHTENAW AND WAYNE COUNTIES

Rates          Fringes

Sign Installer

AREA 1

GROUP 1....................$ 21.78            11.83

GROUP 2....................$ 25.27          11.8375

AREA 2

GROUP 1....................$ 22.03            11.83

GROUP 2....................$ 25.02          11.8375

FOOTNOTE:

a. $132.70 per week, plus $17.80 per day.

SIGN INSTALLER CLASSIFICATIONS:

GROUP 1: performs all necessary labor and uses all tools

required to construct and set concrete forms required in

the installation of highway and street signs

GROUP 2: performs all miscellaneous labor, uses all hand and

power tools, and operates all other equipment, mobile or

otherwise, required for the installation of highway and

street signs

----------------------------------------------------------------

TEAM0247-010 04/01/2017

AREA 1: LAPEER AND SHIAWASSEE COUNTIES

AREA 2: GENESEE, MACOMB, MONROE, OAKLAND, ST. CLAIR, WASHTENAW

AND WAYNE COUNTIES

Rates          Fringes

TRUCK DRIVER (Underground

construction)

AREA 1

GROUP 1....................$ 23.57            19.04

GROUP 2....................$ 23.66            19.04

GROUP 3....................$ 23.87            19.04

AREA 2

GROUP 1....................$ 23.87            19.04

GROUP 2....................$ 24.01            19.04

GROUP 3....................$ 24.20            19.04

PAID HOLIDAYS: New Year's Day, Memorial Day, Fourth of July,

Labor Day, Thanksgiving Day and Christmas Day.

SCOPE OF WORK: Excavation, site preparation, land balancing,

grading, sewers, utilities and improvements; also including

but not limited to, tunnels, underground piping, retention,

oxidation, flocculation facilities, conduits, general

excavation and steel sheeting for underground construction.

Underground construction work shall not include any

structural modifications, alterations, additions and

repairs to buildings or highway work, including roads,

streets, bridge construction and parking lots or steel

erection.

TRUCK DRIVER CLASSIFICATIONS

GROUP 1: Truck driver on all trucks (EXCEPT dump trucks of 8

cubic yards capacity or over, pole trailers, semis, low

boys, Euclid, double bottom and fuel trucks)

GROUP 2: Truck driver on dump trucks of 8 cubic yards

capacity or over, pole trailers, semis and fuel trucks

GROUP 3: Truck driver on low boy, Euclid and double bottom

----------------------------------------------------------------

SUMI2002-001 05/01/2002

Rates          Fringes

Flag Person......................$ 10.10             0.00

LINE PROTECTOR (ZONE 1:

GENESEE, MACOMB, MONROE,

OAKLAND, WASHTENAW AND WAYNE)....$ 18.98            12.17

LINE PROTECTOR (ZONE 2:

STATEWIDE (EXCLUDING GENESEE,

MACOMB, MONROE, OAKLAND,

WASHTENAW AND WAYNE).............$ 17.14            12.17

Pavement Marking Machine

(ZONE 1: GENESEE, MACOMB,

MONROE, OAKLAND, WASHTENAW

AND WAYNE COUNTIES)

Group 1.....................$ 24.89            12.17

Pavement Marking Machine

(ZONE 1: GENESEE, MACOMB,

MONROE, OAKLAND, WASHTENAW

AND WAYNE)

Group 2.....................$ 22.40            12.17

Pavement Marking Machine

(ZONE 2: STATEWIDE (EXCLUDING

GENESEE, MACOMB, MONROE,

OAKLAND, WASHTENAW AND WAYNE

COUNTIES)

Group 1.....................$ 22.89            12.17

Pavement Marking Machine

(ZONE 2: STATEWIDE (EXCLUDING

GENESEE, MACOMB, MONROE,

OAKLAND, WASHTENAW AND WAYNE)

Group 2.....................$ 20.60            12.17

WORK CLASSIFICATIONS:

PAVEMENT MARKER GROUP 1: Drives or operates a truck mounted

striper, grinder, blaster, groover, or thermoplastic melter

for the placement or removal of temporary or permanent

pavement markings or markers.

PAVEMENT MARKER GROUP 2: Performs all functions involved for

the placement or removal of temporary or permanent pavement

markings or markers not covered by the classification of

Pavement Marker Group 1 or Line Protector.

LINE PROTECTOR: Performs all operations for the protection or

removal of temporary or permanent pavement markings or

markers in a moving convoy operation not performed by the

classification of Pavement Marker Group 1. A moving convoy

operation is comprised of only Pavement Markers Group 1 and

Line Protectors.

----------------------------------------------------------------

WELDERS - Receive rate prescribed for craft performing

operation to which welding is incidental.

================================================================

Note: Executive Order (EO) 13706, Establishing Paid Sick Leave

for Federal Contractors applies to all contracts subject to the

Davis-Bacon Act for which the contract is awarded (and any

solicitation was issued) on or after January 1, 2017.  If this

contract is covered by the EO, the contractor must provide

employees with 1 hour of paid sick leave for every 30 hours

they work, up to 56 hours of paid sick leave each year.

Employees must be permitted to use paid sick leave for their

own illness, injury or other health-related needs, including

preventive care; to assist a family member (or person who is

like family to the employee) who is ill, injured, or has other

health-related needs, including preventive care; or for reasons

resulting from, or to assist a family member (or person who is

like family to the employee) who is a victim of, domestic

violence, sexual assault, or stalking.  Additional information

on contractor requirements and worker protections under the EO

is available at www.dol.gov/whd/govcontracts.

Unlisted classifications needed for work not included within

the scope of the classifications listed may be added after

award only as provided in the labor standards contract clauses

(29CFR 5.5 (a) (1) (ii)).

----------------------------------------------------------------

The body of each wage determination lists the classification

and wage rates that have been found to be prevailing for the

cited type(s) of construction in the area covered by the wage

determination. The classifications are listed in alphabetical

order of "identifiers" that indicate whether the particular

rate is a union rate (current union negotiated rate for local),

a survey rate (weighted average rate) or a union average rate

(weighted union average rate).

Union Rate Identifiers

A four letter classification abbreviation identifier enclosed

in dotted lines beginning with characters other than "SU" or

"UAVG" denotes that the union classification and rate were

prevailing for that classification in the survey. Example:

PLUM0198-005 07/01/2014. PLUM is an abbreviation identifier of

the union which prevailed in the survey for this

classification, which in this example would be Plumbers. 0198

indicates the local union number or district council number

where applicable, i.e., Plumbers Local 0198. The next number,

005 in the example, is an internal number used in processing

the wage determination. 07/01/2014 is the effective date of the

most current negotiated rate, which in this example is July 1,

2014.

Union prevailing wage rates are updated to reflect all rate

changes in the collective bargaining agreement (CBA) governing

this classification and rate.

Survey Rate Identifiers

Classifications listed under the "SU" identifier indicate that

no one rate prevailed for this classification in the survey and

the published rate is derived by computing a weighted average

rate based on all the rates reported in the survey for that

classification.  As this weighted average rate includes all

rates reported in the survey, it may include both union and

non-union rates. Example: SULA2012-007 5/13/2014. SU indicates

the rates are survey rates based on a weighted average

calculation of rates and are not majority rates. LA indicates

the State of Louisiana. 2012 is the year of survey on which

these classifications and rates are based. The next number, 007

in the example, is an internal number used in producing the

wage determination. 5/13/2014 indicates the survey completion

date for the classifications and rates under that identifier.

Survey wage rates are not updated and remain in effect until a

new survey is conducted.

Union Average Rate Identifiers

Classification(s) listed under the UAVG identifier indicate

that no single majority rate prevailed for those

classifications; however, 100% of the data reported for the

classifications was union data. EXAMPLE: UAVG-OH-0010

08/29/2014. UAVG indicates that the rate is a weighted union

average rate. OH indicates the state. The next number, 0010 in

the example, is an internal number used in producing the wage

determination. 08/29/2014 indicates the survey completion date

for the classifications and rates under that identifier.

A UAVG rate will be updated once a year, usually in January of

each year, to reflect a weighted average of the current

negotiated/CBA rate of the union locals from which the rate is

based.

----------------------------------------------------------------

WAGE DETERMINATION APPEALS PROCESS

1.) Has there been an initial decision in the matter? This can

be:

*  an existing published wage determination

*  a survey underlying a wage determination

*  a Wage and Hour Division letter setting forth a position on

a wage determination matter

*  a conformance (additional classification and rate) ruling

On survey related matters, initial contact, including requests

for summaries of surveys, should be with the Wage and Hour

Regional Office for the area in which the survey was conducted

because those Regional Offices have responsibility for the

Davis-Bacon survey program. If the response from this initial

contact is not satisfactory, then the process described in 2.)

and 3.) should be followed.

With regard to any other matter not yet ripe for the formal

process described here, initial contact should be with the

Branch of Construction Wage Determinations.  Write to:

Branch of Construction Wage Determinations

Wage and Hour Division

U.S. Department of Labor

200 Constitution Avenue, N.W.

Washington, DC 20210

2.) If the answer to the question in 1.) is yes, then an

interested party (those affected by the action) can request

review and reconsideration from the Wage and Hour Administrator

(See 29 CFR Part 1.8 and 29 CFR Part 7). Write to:

Wage and Hour Administrator

U.S. Department of Labor

200 Constitution Avenue, N.W.

Washington, DC 20210

The request should be accompanied by a full statement of the

interested party's position and by any information (wage

payment data, project description, area practice material,

etc.) that the requestor considers relevant to the issue.

3.) If the decision of the Administrator is not favorable, an

interested party may appeal directly to the Administrative

Review Board (formerly the Wage Appeals Board).  Write to:

Administrative Review Board

U.S. Department of Labor

200 Constitution Avenue, N.W.

Washington, DC 20210

4.) All decisions by the Administrative Review Board are final.

================================================================

END OF GENERAL DECISION