RFP 20-031 – ADDENDUM No. THREE (003)

- Page 8, Sec. III, Summary of the Project schedule is changed to read:

| Design Award | March May 2020 |
| --- | --- |
| CMAR Construction Award | May October 2020 |
| Conceptual and Schematic Design and Community Process | May 2020 – November December 2020 |
| Design Development through Construction Documents | November December 2020 – July September 2021 |
| Permitting | July August 2021 – November 2021 January 2022 |
| Construction | November 2021 – April 2023 January 2022 - June 2024 |
| Furniture, Fixtures & Equipment and Relocation | April 2023 – May 2023 June 2024 - July 2024 |

2. Page 11, Sec. IV.A.6. Paragraph #6, is changed to read,

The second and third meetings and PFRC reviews shall occur during the Schematic and Design Development Phases. In these meetings the Contractor shall present modifications requested by the PFRC to obtain PFRC approval.

3. Page 13, Sec. IV.B.1.d, delete this section and replace with:

  - Code and Zoning Requirements and County Standards: Review the Project Zoning Requirement Summary (Attachment B6), identify any other zoning requirement, meet with and analyze the requirements of Arlington County Code and Zoning Officials and participate in consultations with such authorities to ensure that the Project’s Concept Design meets all applicable code requirements.  Identify all state, local and federal jurisdictional permit and approval processes for the project. https://building.arlingtonva.us/resource/about/zoning/

Analyze information provided and develop Project Documents capturing Transit requirements ensuring compliance with Arlington County Infrastructure Design Standards, and other applicable standards.  https://building.arlingtonva.us/resources/design-standards-guidelines/

4. Page 14, Sec. IV.B.1.i, revise as follows:

- i. Design-to-Budget – The Contractor shall review the construction cost estimate for the proposed Conceptual Design (Attachment B8) and confirm that it includes all the project costs and propose the Design-to-Budget amount for County approval. Should the County proceed with the Optional Task (Section B.3.h. B.1.h), the Contractor shall estimate the additional cost impact to be included in the Design-to Budget.

5. Page 35, Sec. VI.1, revise as follows:

Exhibit B – Scope of Work

AttachmentB-1 – Conceptual Site Drawings Attachment B-2 – Channel Improvement Drawings Attachment B-3 – Conceptual Architectural Drawings - Revised

Attachment B-4 – Conceptual Program

Attachment B-5 – Conceptual Narrative

Attachment B-6 – Zoning Requirements

Attachment B-7 – Review Comments

Attachment B-8 – Project Cost Estimate (provided to successful Offeror)

6. Page 63, Attachments, Add a new page:

ATTACHMENT – B-8 CONCEPTUAL COST ESTIMATE (Document to be issued Separately)